## Prev Years Activities & Actions
[5 empty] | Relevant coordination and cooperation activities | [12 empty] | Action or processes arising
| "Unique identifier for each row of the sheet. xxxx/00n for an activity xxxx/00n/ A0m for action xxxx refers to the publishing organisation or license group; n and m refers to numbers | Lead licensee for the action or activity (not licence group) | Licensees and other stakeholders with whom collaboration was/is being carried out. | What year was the activity added to the coordination register | Details of the activity (could be an activity from a project or an activity that is used in multiple projects) along with its objective. Only activities that improve the economy and efficient of the whole electricity system is to be considered. Register is of activities in progress or completed, not planned. Explanation of the activity takes precedence over the project description |  | In progress, Not taken forward, Complete | Latest stage / Update since the last publication / comments | When was a decision made to act upon a challenge/need. This could include the date when analysis for options was initiated. | Details of why it is relevant to whole system. | Links to reports of the project or activity | Description of any data that was shared. Include the format of the data, if applicable, and highlight any data that cannot be widely shared due to commercial sensitivity. | Links to the data not the project/activity | Description of any data that was shared. Include the format of the data, if applicable, and highlight any data that cannot be widely shared due to commercial sensitivity. |  |  |  | Details of the action/ process | Rough date of initiation of the action/ process | New, Improving, Mature, BaU | Reference to the activity in the register that resulted in this action/ process (not to be confused with internal order or project numbers)
Type | Unique ID | Licensee | Collaborating Licensees and other stakeholders | Year activity added | Activity Title | Description of the coordination/ cooperation activity | Activity Status | Latest stage/ update/ comments (if any) | Coordination Activity Initiation Date (dd/mm/yyyy) | Whole System Relevance Of The Activity | External Links To Reports On The Activity (if available) | Description Of Data (who shared the data) {widely shared/ restricted sharing} | External Links For Data | Impact Of The Activity On The Whole System | Impact Of The Activity On Licensee | Recommended Next Stage Of TheActivity | JustificationForRecommendation | Action Or Process Description | Action Or Process Initiation Date (dd/mm/yyyy) | Action Status | ActivityReference
Co-ordination and cooperation activity | SSEN/001 | SSEN Transmission | SSEN-D | 21/22 | Coordination with SSEN Distribution | Joint discussions with SSEN Distribution to capture their need to uprate transformer capability on sites with planned transmission network reinforcements to enable a coordinate network development as demonstrated in East Coast 132kV Upgrade (LT225) | In progress | 2026-12-21 | 2021-01-03 | Ensures better coordination and better utilisation of resources resulting in overall whole electricity system benefits. | N/A | Business case with technical information (SSEN Transmission) [restricted sharing]; | N/A | The impact on the whole system is positive as a coordinated approach results in efficient capacity sizing of assets and also better overall resource efficiency. | The impact on the licensee is positive as a coordinated approach results in resource efficiency. | Recommend ongoing co-ordination with SSEN Distribution for planned transmission reinforcements at GSP sites which impact SSEN Distribution. | This decision would enable better utilisation of resources and achieve more efficient outcomes.
Related Action | SSEN/001 | SSEN Transmission | SSEN-D | 21/22 | [13 empty] | New Business Case template incorporating the need to explore whole system options. This will inform future working with other network licensees as a BaU activity. | 2021-01-03 | Business As Usual | SSEN/001
Co-ordination and cooperation activity | SSEN/002 | SSEN Transmission | SPEN | 21/22 | Cross-boundary asset intervention plans | Preliminary meeting to agree future meetings to ensure we align our cross-boundary asset intervention plans for the T3 period | Complete | N/A | 2021-10-21 | If we coordinate our planned activities at cross-boundary circuits, we can ensure the most efficient delivery process that will achieve the outputs at the lowest cost to the consumer. | N/A | No data shared at this preliminary meeting | N/A | The impact is neutral at this time, but we expect the eventual outcome to be positive, once cross-boundary projects have been identified and coordinated | The impact is neutral at this time, but we expect the eventual outcome to be positive, once cross-boundary projects have been identified and coordinated | Establish quarterly coordination meetings, once development of the T3 business plans commence | Having coordination meetings with other network licensees like SPEN will ensure efficient project planning delivery across our network boundaries.
Related Action | SSEN/002 | SSEN Transmission | SPEN | 21/22 | [7 empty] | Power system analysis results for 132kV transmission OHL loading (SSEN Transmission) [restricted sharing) Future Generation and Demand scenarios for relevant GSPs (SSEN Distribution) [restricted sharing] | [5 empty] | The action is to offer SSEN Distribution a new GSP at Edinbane so that they can connect customers to the new site. | 2021-01-04 | New | SSEN/002
Co-ordination and cooperation activity | SSEN/003 | SSEN Transmission | SPT; NGESO, SPD, SSEN Distribution | 21/22 | Abernethy/Burghmuir investment review | Under the Regional Development Program approach, completed a coordinated review of proposed transmission investment works to accommodate new battery customer connections at Abernethy and Burghmuir. This required a risk based/probabilistic approach to better understand the risk of constraints recognising the unique operating philosophy of battery system storage technology. | In progress | Latest update as of Feb 2025 | 2019-01-07 | Review of options across transmission and distribution networks to resolve potential transmission constraints. | No |  | N/A | Positive - broad assessment of all Transmission and Distribution related options, resulting in the most cost effective outcome. | Positive as it supports timely investment decision making and customer connected in line with contracted dates. | Develop Regional Development Plan (RDP) to accommodate local growth and coordinate with asset replacement plans. | It is expected that a pro-active approach through the RDP will identify efficient solutions for customer connections in the region ahead of transmission infrastructure investment.
Related Action | SSEN/003 | SSEN Transmission | SPT; NGESO, SPD, SSEN Distribution | 21/22 | [13 empty] | Updated Feb 2025: The assessment of the requirement for this reinforcement under probabilistic CPAs will be conducted as a part of G2tWQ re-assessment (connection reforms). In RIIO-T3, as a part of CP2030 submissions, a paper is being put forward to Ofgem to indicate that a derogation may be required in T3 if a scheme with firm connection security still requires the reinforcement as enabling works post G2tWQ re-assessment. For non-firm access, the network is proposed to be managed using an Active Network Management (ANM Scheme). Updated 2022: Further development of probabilistic planning methodology and exploring how this approach can be applied to other parts of the network where there is value to whole system in doing so. | 2020-01-12 | Improving | SSEN/003
Co-ordination and cooperation activity | SSEN/004 | SSEN Transmission | SSEN-D; NGESO | 21/22 | Moving customers from Dunvegan to Edinbane | Discussions with SSEN Distribution and ESO on procedure to move customers from Dunvegan to Edinbane to resolve conflict on distribution and transmission route corridors. This was to achieve cost efficiency in the connection arrangement. | Complete | 2026-12-21 | 2021-01-04 | Cost effectiveness to customers and distribution network operator |  | Technical Report with cost data and alternative solutions shared (SSEN Transmission) [RESTRICTED SHARING]. SSEN Distribution provided indicative costs data on distributions options (SSEN Distribution) [Restricted Sharing]. | N/A | Positive reduction on Customer works which in turn translates to lower cost of connection. | Positive, avoided costs in Transmission infrastructure. | Consider potential GSP relocation for future embedded generators that trigger significant works at existing GSP sites. | Potential to provide costs savings for all parties involved.
Related Action | SSEN/004 | SSEN Transmission | SSEN-D; NGESO | 21/22 | [13 empty] | Establish a quarterly coordination meeting between SSEN Transmission & SPEN to discuss the development of our T3 non-load business plans to establish any cross-boundary activities. 2025 update: ceased meetings when it became clear that the T3 period would not involve any major non-load cross-boundary activities. | 2021-01-10 | Mature | SSEN/004
Co-ordination and cooperation activity | SSEN/005 | SSEN Transmission | SPEN; NGET; SSEN-D; Users, Ofgem, ENA, Trade bodies | 21/22 | Advocating for TNUoS reform | Advocating for reform to Transmission Network Use of System (TNUoS) charges to remove barriers to renewable generation development in the north of Scotland whilst ensuring charges do not hinder the progression of our business objectives and the transition to net zero. This includes representing SSEN Transmission on industry forums including Ofgem's Access and Forward looking Significant Code Review. | Complete | The latest update on this work as of March 2025 | 2020-01-07 | Our evidence based work on this area, monitors and tracks the effect that TNUoS has on users and how TNUoS impacts system investment and operation at both Distribution and transmission. This includes advocating for reform not only for transmission connected generation but also at distribution (Ofgem's Access SCR minded to position). A key part of this work is also considering the impact on consumers and ensure society reaches net zero efficiently at least cost. | https://www.ssen-transmission.co.uk/information-centre/tnuos/ | Shared data analysis (developers and SSEN Distribution) [widely shared]. Collaboration with industry bodies and wider stakeholders. | https://www.ssen-transmission.co.uk/information-centre/tnuos/ | Our work in this area has led us to be trusted source of information that stakeholders rely on. We have seen a positive change in direction by Ofgem publishing a call for evidence on TNUoS reform and it is expected that a wide ranging review will take place. | Positive impact on SSEN Transmission in particular around enhancing our stakeholder engagement and our corporate image. Working to stabilise the cost of using the network will also provide further investment certainty for both developers and the required network construction. | Recognition from Ofgem on issues with TNUoS indicates that reform will take place, we will continue our work and advocacy on this area. Through our work on this we have also identified that there are other facets of the electricity markets that directly effect TNUoS, we plan to further explore and analyse the electricity market in further detail. | Grid charging, access and markets play a vital part of ensuring that we can deliver our business plan efficiently. It is important for us to continue to monitor change in this area and advocate where appropriate the requirements for our business, stakeholders and wider society.
Co-ordination and cooperation activity | SSEN/006 | UK Gov | SPEN; NGET; BEIS; NGESO | 21/22 | Offshore Transmission Network Review | SSEN Transmission has been actively involved in the Offshore Transmission Network Review initiated by the UK Government. Our aim is to drive policy position and ensure an efficient holistic network design. | Complete | The latest update on this work as of March 2025 |  | A holistic whole system approach to offshore network design is critical to address the barriers that the current regime presents to connection of high volumes of wind required to meet net zero | https://www.nationalgrideso.com/document/239466/download | Interface location points and cost data shared (NGESO) [restricted sharing] | N/A | This project will have a positive impact on the whole system as it will ensure an efficient coordinated development and delivery of the offshore transmission network across Great Britain | The project has a positive impact on SSEN Transmission, in that it will enable us to connect huge volumes of offshore wind to the network in an efficient and economic manner. | The ESO to publish the outcomes from the working group. | This project is important as it will ensure efficient development and delivery of the offshore transmission network which is essential to enable the connection of huge volumes of offshore wind required to meet net zero.
Co-ordination and cooperation activity | SSEN/007 | Other | SPEN; NGET; NGESO | 21/22 | Consultation feedback for technical codes | SSEN Transmission has provided its views on the NGESO's consultation on simplification, digitalisation and consolidation of technical codes (Grid Code and Distribution code). | Complete | The latest update on this work as of March 2025. 4/3/26 No progress since last update | 2021-01-09 | This project is important as it supports the Energy Code Review and addresses some of the challenges of the existing codes to enable whole system thinking. | No | Responded to the questionnaire on a number of issues and things that should be done to enable the simplification and consolidation of technical codes to benefit the total system. (NGESO) [restricted sharing] | N/A | We expect a positive impact on whole system | Positive impact on SSEN Transmission particularly around enhancing stakeholder engagement on issues that impact us and our stakeholders | We have nominated representatives from different parts of the business to participate in working groups to help in defining the scope and implementing the changes | Technical codes will play a critical role in how we develop and operate the network for net zero. We are keen to be actively involved in the simplification and consolidation of technical codes to ensure that its done in a manner that benefits whole system.
Co-ordination and cooperation activity | SSEN/008 | SSEN Distribution | SSEN-D | 21/22 | Resilient as a Service project | Discussions with SSEN Distribution on how their Resilient as a Service project would benefit the transmission network in system restart and relieving network constraints. | Complete | Feb-21. 6/3/26 Complete | 2021-01-01 | If successfully implemented and scaled up this activity can help to reduce network constraints as well as support system restart. | https://ssen-innovation.co.uk/raas/ | SSEN Distribution has shared with SSEN Transmission project conceptual designs [widely shared] | N/A | Overall this activity will have positive impacts as it will help to relieve constraints on the network, provide support to system restart and potentially allow for connection of more renewable energy sources | If scaled up, this activity will support the overall resilience of the network | Continue to cooperate and support SSEN Distribution on this activity in terms of data sharing to ensure that cross operational impacts are properly addressed. | We are a network for net zero and will support initiatives that promote increase in connection of renewable generation to the network and enhancing network resilience.
Co-ordination and cooperation activity | SSEN/009 | SSEN Transmission | SSEN-D | 21/22 | Argyll renewable generation | Discussions with SSEN Distribution on a whole system solution between transmission and distribution to support connection of renewable generation in Argyll | Complete | The latest update on this work as of March 2025 | 2021-01-06 | A combined Transmission and Distribution solution will result in an efficient and economical solution that minimises costs to consumers | https://www.sse.com/news-and-views/2022/03/argyll-transmission-network-upgrade-to-support-transition-to-net-zero/ | Options and costs used for cost benefit analysis [restricted sharing] | N/A | Positive impact on whole system as the combined transmission and distribution solution provides an efficient and economical solution | Discussions about cost recovery options for the distribution works are underway since SSEN Distribution does not have allowance for the project. | The activity will be implemented as part of the wider Argyll project. The outcome of cost recovery of distribution works will inform future working on projects of this nature. | The activity has been adopted as part of the wider Argyll project because it’s the right thing to do as it results in efficient and economic whole system solution.
Related Action | SSEN/009 | SSEN Transmission | SSEN-D | 21/22 | [13 empty] | A clear process of dealing with projects that support a combined transmission and distribution whole system solution addressing issues of who should deliver the distribution works, how should they be funded and ownership | 2021-01-01 | Business As Usual | SSEN/009
Co-ordination and cooperation activity | SSEN/010 | ENA | SPEN; NGET; BEIS; NGESO | 21/22 | ENA Workstreams | SSEN Transmission has taken an active role in different workstreams facilitated by the Energy Network Association. The work has included the development of tools like whole system cost benefit analysis required to enable a consistent approach to whole system. | Complete | The latest update on this work as of March 2025 |  | The workstreams are essential to enable a consistent approach to whole system across network licensees. | https://www.energynetworks.org/creating-tomorrows-networks/open-networks/ | The workstreams are working on what is required to enable efficient data sharing between network licensees. | N/A | This has a positive impact in that it will ensure consistency in the whole system approach to the development and operation of the network. | SSEN Transmission will benefit from knowledge, data and information sharing with other network licensees around whole system. | SSEN Transmission will continue to be actively involved in the workstreams and facilitate implementation of processes and tools required to enable whole system working. | ENA workstreams are important as they provide a platform to develop processes and tools which will ensure a consistency in taking whole system approach and coordination activities across network licensees.
Co-ordination and cooperation activity | SSEN/011 | SSEN Transmission | SSEN-D; NGET; SPEN; SGN, NGESO, BEIS, Ofgem, Local Authorities | 21/22 | Whole System Strategy & Annual Report | Coordination activities with SSEN Distribution, NGET, SPEN and other stakeholders in the development of our whole system strategy and annual report. | Complete | The latest update on this work as of March 2025 | 2021-01-04 | This is relevant to whole system because by working with other network licensees and stakeholders, SSE Transmission is able to share its knowledge and experience in its approach to whole system and in return it gets feedback that it can use to make relevant changes to its approach to whole system which will benefit the total system. | The link to reports will be added when the whole system page is active | SSEN Transmission has shared presentation slides of its whole system strategy and annual report [Widely sharing] | N/A | Positive impact on whole system as other network licensees and stakeholders learn from SSEN Transmission on how we are embedding whole system thinking within our business with the aim of making it a BaU activity. | By interacting with stakeholders and other network licensees on our whole system strategy and annual report, we show leadership in the industry but we also get the feedback we need to improve our whole system approach to investment decision making. | The next stage is to publish the revised whole system strategy and our first whole system annual report this year. | These activities are necessary to ensure coordinated, efficient and economic whole system investment decision making.
Co-ordination and cooperation activity | SSEN/012 | SSEN Transmission | SSEN-D; NGESO | 21/22 | Shetland, Orkney and Western Isles transmission projects | Coordination activities with SSEN Distribution and ESO on the Shetland, Orkney and Western Isles transmission projects | Complete | The latest update on this work as of March 2025. 3/6/26 Superseded by newer activities | 2012-01-09 | This is relevant to whole system because apart from connecting renewable generation from the Islands to the mainland, SSEN Transmission is working with SSEN Distribution to ensure that these projects contribute to security of supply, decarbonisation of the islands and resolving local electricity asset condition issues. | https://www.ssen-transmission.co.uk/projects/shetland/ | SSEN Transmission has shared with SSEN Distribution and ESO technical reports and costs [Restricted sharing] | N/A | Positive impact for both transmission and distribution networks to fulfil their licence obligations and connection of renewable generation to the grid is critical to meeting net zero | Positive impact on SSEN Transmission as the coordinated approach results in an efficient and economic investment on the network. | Continue with the coordination activities between SSEN Transmission and SSEN Distribution in supporting economic development in the Scottish Islands through connection of renewable generation to the grid and improving demand security | These activities are necessary to ensure coordinated efficient and economic whole system investment decision making.
Related Action | SSEN/012 | SSEN Transmission | SSEN-D; NGESO | 21/22 | [13 empty] | The action is to continue with the coordination activities in prioritising, scheduling and sequencing of activities as the projects progress into delivery. . | 2022-03-31 | Business As Usual | SSEN/012
Co-ordination and cooperation activity | SSEN/013 | SSEN Transmission | SSEN-D | 21/22 | Glasvaar wind farm | Discussions with SSEN Distribution on options to minimise network reinforcement costs for connecting Glasvaar wind farm to the network | Closed | Mar-21. 4/3/26 No progress since last update | 2021-03-16 | SSEN Distribution involvement could drastically reduce network reinforcement costs | N/A | SSEN Transmission has shared with SSEN Distribution the location, transmission entry capacity and costs [Restricted sharing] | N/A | Positive impact on whole system as a combined transmission and distribution solution will result in cost savings | Positive impact on SSEN Transmission as a combined transmission and distribution solution will result in reduced network reinforcement costs thereby supporting connection of renewable generation to the network and contributing to net zero | Discussions with the customer on the potential options and associated benefits. | The next stage will depend on the customer's decision as to which option to progress with.
Related Action | SSEN/013 | SSEN Transmission | SSEN-D | 21/22 | [13 empty] | A quarterly meeting group has been established by Whole System managers from SSE, SP, NGT and some DNOs | 2021-04-01 | Business As Usual | SSEN/013
Co-ordination and cooperation activity | SSEN/014 | SSEN Transmission | University of Strathclyde, National HVDC Centre | 22/23 | Preferred Solutions to perform for Lower levels of Fault Current on AC networks (PSL-FC) | Preferred Solutions to perform for Lower levels of Fault Current on AC networks (PSL-FC). To simulate a future electrical network where the fault current spike is marginal but prolonged and evaluate how present P&C products function and respond. Based upon the findings it will determine if a Protection and Control (P&C) solution can be further developed to address the potential future network issues. This project aims to investigate how effective and reliable current P&C equipment is on a future electricity network, which has even more renewable generation and power electronic equipment, via a combination of network simulation and open-loop device trials. It is also the aspiration to determine new tests and validation processes for the P&amp;C equipment in the future transmission system environment of low fault currents. Research would also be conducted into the shape and structure of new P&C operating processes and protocols to help accommodate the transition of the network towards net-zero. | In progress | Feb-26 Project has progressed over the last 12 months. Relays are now in place and the technology is being installed at site. All involved collaborators are still included | 2022-06-30 | By understanding the protection and control requirements needed for the network to operate with the increase in renewable generation sources will reduce the potential for disruption to the electrical energy supply. | https://smarter.energynetworks.org/projects/nia_shet_0033/ | Data shared with University of Strathclyde and National HVDC Centre. All results of the project will be disseminated via ENA Smarter Networks portal and CIGRE P&C conferences and papers | N/A | Positive impact. Reducing the potential for protection and control issues to affect the electrical energy supply to the UK. This would impact both Generation, Transmission and Distribution as well as knock on effect to Gas operators | Positive impact as understanding the future protection & control needs for the network allows for better planning. | Installation of equipment into the field to allow for comparison with the lab data | Evidence that the simulated lab results are confirmed by the field data will provide confidence that the technology can be applied to the future network.
Related Action | SSEN/014 | SSEN Transmission | University of Strathclyde, National HVDC Centre | 22/23 | [13 empty] | Initiate projects to resolve operability issues in the north of Scotland following approval from Ofgem The action is to continue with the coordination activities with NGESO on the previous system operability issues. 2025 update: Continuing to resolve operability issues with coordination activities with NESO and SPEN in an evolving network. | 2024-01-03 | Business As Usual | SSEN/014
Co-ordination and cooperation activity | SSEN/015 | SSEN Transmission | SPEN; NGESO; Venders/manufacturers | 22/23 | System power quality issues | Coordination activities with NGESO and SPEN on system power quality issues following unusually high levels of harmonic distortion observed in the South West region. In particular, understanding the causes of the harmonic distortion and how to reduce them. | In progress | Latest update as of March 2026 - coordination is ongoing between NESO and SPEN regarding the system power quality issues in the south west whilst we await a harmonic filter to be installed on our network to resolve the issue. Initial design and study work has been undertaken with further refinement due in the next few months. The filter will not be installed for another few years so ongoing coordination will need to continue. | 2022-01-04 | Through the coordination activities with other network licensees as well as the system operator, a holistic approach is being taken to resolve these power quality issues which will benefit the operability of the total electricity system | N/A | Received harmonic data from SPEN [restricted sharing] | N/A | This has a positive impact as the solutions to these power quality issues will ensure the operability of the total electricity system | The knowledge sharing from these coordination activities has helped us to come up with the most efficient and economic solutions to resolve these emerging system power quality issues. | SSEN Transmission has submitted a project to Ofgem which will mitigate the impact of these system power quality issues. SSEN Transmission are progressing with a project which will mitigate the impact of these system power quality issues. Coordination with NGESO [and SPT will be maintained as an affected TO]. | To maintain the operability of the electricity system
Related Action | SSEN/015 | SSEN Transmission | SPEN; NGESO; Venders/manufacturers | 22/23 | [13 empty] | Coordinate with the HVDC centre on the design and simulation of a feasible controller. 2025 update: Coordinate with DESNZ on future opportunities for physical demonstration. | 2023-01-04 | Improving | SSEN/015
Co-ordination and cooperation activity | SSEN/016 | SSEN Transmission | NGET; National HVDC Centre | 22/23 | Project Aquila | Project Aquila - Coordination activities with NGET on HVDC multi-vendor interoperability development and demonstration. Currently HVDC converters between different manufactures cannot work with each other. This has been recognised by BEIS as a pathfinder project in July 2022. A new control model is being developed by the HVDC centre to work as an "adapter" to allow a control over converters by different manufactures. Updated March 2025: This was initially recognised by BEIS as a pathfinder project in July 2022. Coordination activities with NGET on HVDC multi-vendor interoperability development and demonstration. Coordination with DESNZ and major suppliers related to proving interoperability in the lab environment at NHVDC centre. Due to descope activities in March 24, the project now concentrates on proving interoperability in supplier replica models with the physical demonstration at Peterhead placed on hold. | In progress | Update as of March 2025: Project Aquila was rescoped in March 2024 with the physical demonstration element removed. The project has continued to evidence interoperability using NHVDC models as well as investigate the commercial readiness of the technology introduction. It is expected that this body of work will be completed in 2025. Update as of Feb 2026. The project has successfully proven interoperability with 2x vendors models. Additional work to complete the work on a third vendor model is ongoing and is expected to complete in mid 2026 | 2022-01-09 | Through the engagement activities from GB Interoperability Workgroup with other network licensees, SSEN Transmission, through HVDC Centre, is able to share its knowledge and experience in its approach to whole system and in return it gets feedback that it can use to make relevant changes to its design which will benefit the total system. | https://www.hvdccentre.com/our-projects/aquila-interoperability-package/ | [Restricted sharing] Models and project learning is continuously shared with NGET | N/A | Once multi-vendor interoperability is proven, this can be deployed to HVDC transmission projects in the future. | This would potentially reduce the number of HVDC convertor stations required by connecting HVDC links to a multi-terminal switching stations. | SSEN Transmission to continue engagement and move towards Project Assessment | This project is important as it will enable interoperability development and benefit the delivery of the offshore transmission network by potentially reducing the connection to huge volumes of offshore wind required to meet net zero.
Related Action | SSEN/016 | SSEN Transmission | NGET; National HVDC Centre | 22/23 | [13 empty] | Coordinate with the HVDC centre on the design and simulation of a feasible controller. 2025 update: Coordinate with DESNZ on future opportunities for physical demonstration. | 2023-01-04 | Improving | SSEN/015
Co-ordination and cooperation activity | SSEN/017 | SSEN Transmission | SPEN; NGESO; Venders/manufacturers | 21/22 | System operability issues | Coordination activities with NGESO and SPEN on system operability issues following a number of system disturbances in Scotland. In particular, understanding the causes of sub synchronous oscillations and how to resolve them | In progress | Latest update as of March 2026 - coordination between NESO and SPEN is ongoing regarding the system operability issues. The group are constantly investigating the causes of sub sychronous oscillations as the network evolves and more invertor based. | 2021-01-10 | Through the coordination activities with other network licensees as well as the system operator, a holistic approach is being taken to resolve these operability issues which will benefit the security of the total electricity system |  | Shared models and technical reports with ESO [restricted sharing] | N/A | This has positive impact as the solutions to these operability issues will ensure the security of the total electricity system | The knowledge sharing from these coordination activities has helped us to come up with the most efficient and economic solutions to resolve these emerging system operability issues. | SSEN Transmission has submitted a number of projects to Ofgem which will mitigate the impact of these system operability issues. SSEN Transmission are continuing to work with NGESO on coordination activities on system operability issues. The System Performance team have two standing calls per week to discuss the system studies both partners are undertaking to maintain an understanding with regards to previous system operability issues. | To maintain the security of the electricity system
Related Action | SSEN/017 | SSEN Transmission | SPEN; NGESO; Venders/manufacturers | 21/22 | [13 empty] | Ensure the results of the project are moved into BaU operation | 2026-07-03 | Mature | SSEN/017
Co-ordination and cooperation activity | SSEN/018 | SSEN Transmission | NGESO | 22/23 | TOTEM Extension (Transmission Owner Tools for EMT (Electromagnetic Transient) Modelling) | TOTEM Extension (Transmission Owner Tools for EMT (Electromagnetic Transient) Modelling). Continuation of NIA_SHET_0032 TOTEM project to complete the development and associated validation of a full-scale model of the GB Transmission System in EMT PSCAD (Power System Computer Aided Design) simulation software. TOTEM is focused on the development of innovative tools and resources for power system modelling and analysis. It will produce a model that can mimic large volume power electronics and enable formulation of mitigation measures to future proof the GB network associated with the energy transition. The end product will be a valuable modelling tool which will require validation and improvement through studying actual system disturbances. | Complete | 2026-07-23 | 2022-05-17 | Deliver tools for PSCAD model manipulation for the whole GB network and analysis that will support the TOs in their use of the GB model. | https://smarter.energynetworks.org/projects/nia_shet_0035/ | [Widely shared] Network models | N/A | Positive impact. To be able to actively model the current and future GB network. All TO's will be able to use the tools and Distribution Network Owner (DNO) will be able to see the results of the project and gain learning. | Positive impact. To be able to actively model the current and future SSEN Transmission network | The end product will be a valuable modelling tool, however it will need to be validated and improved through studying actual system disturbances. [23/24 UPDATE] Project has completed and tool to be used in BaU. Continued dialogue with other network users on the suitability of the TOTEM tool as well as areas of improvement | Enable future proofing of the network. [23/24 UPDATE] Tool to be employed in a BaU environment to prove the worth of the project
Related Action | SSEN/018 | SSEN Transmission | NGESO | 22/23 | [13 empty] | Ensure the recommended next stage activity (model validation and improvement through study of actual system disturbances) is performed and the results distributed [23/24 UPDATE] The tool is to be used to investigate system disturbances | 2024-02-28 | Business As Usual | SSEN/018
Co-ordination and cooperation activity | SSEN/019 | SSEN Transmission | SPEN; NGET | 22/23 | CAT Database Working Group | A working group has been set up between the three GB TOs to develop a master Carbon Asset (CAT) Database which contains greenhouse gas intensity factors for specific assets to allow for more accurate reporting on embodied carbon emissions. Shared between the three TOs and all DNOs. Also shared with supply chain. | In Progress | Latest update Feb 2025. As a result of this work, the three transmission network licences will have a consistent methodology for calculating embodied carbon emissions in transmission projects. The CAT database is being updated to ensure it is consistent with latest carbon emissions factors - with work being shared amongst the TOs to ensure efficiency. Updating database / Ongoing / as of February 2026 | 2019-01-01 | As a result of this work, the three transmission network licences will have a consistent methodology for calculating embodied carbon emissions in transmission projects. The CAT database is being updated to ensure it is consistent with latest carbon emissions factors - with work being shared amongst the TOs to ensure efficiency. | N/A | Shared between the three TOs and all DNOs. Also shared with supply chain. | N/A | This ensures a consistent methodology is applied across all TOs and the regular updates will allow opportunities to share learnings. This group helps improve carbon reporting across the transmission system. It also provides a consistent database for the supply chain to use when providing transmission related embodied carbon data. | This database has provided us with the necessary data to start reporting on project level embodied carbon. The continued shared learning will ensure we stay aligned with other TO's whilst improving the accuracy of our carbon reporting. | The key next step is to finalise the update and then update all carbon tools to ensure the carbon factors are up to date. | These activities are necessary to allow a co-ordinated approach to embodied carbon emissions reporting.
Related Action | SSEN/019 | SSEN Transmission | SPEN; NGET | 22/23 | [13 empty] | Share add-ins to the master database | 2022-01-12 | Business As Usual | SSEN/019
Co-ordination and cooperation activity | SSEN/020 | SSEN Transmission | SPEN; NGET | 22/23 | Substation Energy Consumption Working Group | A working group has been set up between the three GB TOs to collaborate and share knowledge on substation energy consumption. The aim of the group is to improve the accuracy of substation energy consumption data which is required to calculate part of our operational emissions. | Complete | Latest update as of Feb 2025 | 2022-01-06 | Through this working group, the GB TO's are applying a joint approach to methodology development by sharing knowledge on existing methods as well as discussing potential new methods which could be explored further. | N/A | Knowledge sharing has occurred over MS Teams meetings, no data has been shared yet. | N/A | This will allow for more accurate reporting on operational emissions across the transmission system and will ensure a coordinated approach is applied amongst the three TO's. | Knowledge sharing from the working groups has given us a sense of the accuracy of our current methodology and has provided us with potential alternative methods which can be further explored. | The next step is for SPEN to provide us with a detailed description of the new methodology they are currently exploring in the format of a presentation. | These activities are necessary to allow a coordinated approach to substation energy consumption emissions reporting.
Related Action |  | SSEN Transmission | SPEN; NGET | 22/23 | [13 empty] | Exchange data and idea on methodologies with other stakeholders | 2023-01-02 | Improving | SSEN/020
Co-ordination and cooperation activity | SSEN/021 | SSEN Transmission | SPT; NGET; SSEN-D; Users, Code Administrators, SSE Renewables, SSE Business Services | 22/23 | Energy Security Bill coordination | Co-ordination activities and insight sharing on BEIS and Ofgem Energy Code Reform proposals in Energy Security Bill | Complete | The latest update on this work as of March 2025 | 2022-01-04 | Enables cross vector and cross fuel learning to ensure BEIS benefits case realised (Impact Assessment states benefit £1.6m p/a efficiency saving for industry through reforms) | N/A | N/A | N/A | Positive impact - seeks to take learnings from current code governance and to apply to reforms and maximise whole system opportunity of reforms | Positive impact - seeks to take learnings from current code governance and to apply to reforms and maximise whole system opportunity of reforms | Continue SSENT's Stakeholder Engagement Plan for ECR | Plan to date has brought value and insight through bi-lateral meetings
Related Action |  | SSEN Transmission | SPT; NGET; SSEN-D; Users, Code Administrators, SSE Renewables, SSE Business Services | 22/23 | [13 empty] | Review reporting requirements | 2022-01-12 | Improving | SSEN/021
Co-ordination and cooperation activity | SSEN/022 | SSEN Transmission | NGET; SPT; ENA, Users | 22/23 | Code Modifications | Co-ordination activities to further code modifications in CUSC, STC, SQSS, Grid Code that meet the code objectives of safe and reliable system and consumer benefit etc., and overarching goal of net zero | Complete | The latest update on this work as of March 2025 | 2022-01-04 | Enables co-ordinated whole system approach to code modifications, aligned positions, to fulfil the relevant code objectives and efficient code governance procedures | https://www.energynetworks.org/creating-tomorrows-networks/open-networks/ | ENA Open Networks monthly publication of Steering Group Report - Annex of code modifications | N/A | Positive impact to enable fulfilment of the relevant code objectives and efficient code governance procedures | Positive enables alignment and learning from TO's and users, and assessment of code modifications against the code objectives and objectives of ENA Open Network project | Maintain activities and utilise learnings to inform SEN/023 - Energy Code Reform | Ensure learnings from current code governance and the opportunities and limitations inform advocacy position for Energy Code Reform
Related Action |  | SSEN Transmission | NGET; SPT; ENA, Users | 22/23 | [13 empty] | Maintain activities and utilise learnings to inform SSEN/023 - Energy Code Reform | 2023-01-03 | Business As Usual | SSEN/022
Co-ordination and cooperation activity | SSEN/023 | SSEN Transmission | SPEN; NGET | 22/23 | Project Waste Reporting Working Group | A working group has been set up between the three GB TO's to collaborate and standardise project waste reporting (where possible). The aim of the group is to promote data collection consistency and to reduce administrative efforts for our supply chain partners. | Complete | Nov-22. 3/6/2 Complete | 2022-01-10 | Through this working group, the GB TO's are sharing knowledge on existing reporting requirements as well as discussing potential new requirements which could be explored further. | N/A | Knowledge sharing has occurred over MS Teams meetings. Waste reporting templates for each TO have also been shared under restrictive access. | N/A | This will ensure a coordinated approach is applied amongst the three TO's. | Positive impact - improved coordination and standardisation. | The next step is for all TO's to collaborate on a shared file in which we can review our reporting requirements. | These activities are necessary to allow a co-ordinated approach to waste reporting.
Related Action |  | SSEN Transmission | SPEN; NGET | 22/23 | [13 empty] | Maintain activities and utilise learnings to inform SSEN/022 - Energy Code Modification management | 2023-01-03 | Business As Usual | SSEN/023
Co-ordination and cooperation activity | SSEN/024 | SSEN Transmission | SSEN-D; local council, communities and developers | 22/23 | Orkney Whole System Study | Orkney Whole System Study - coordinating with SSEN Distribution and developers to determine the optimal option of connecting renewable energy generation on Orkney. | Complete | 2026-01-23 | 2022-01-10 | Establishing working relationships with SSEN Distribution, local council and communities to improve infrastructure and connections on the islands surrounding Scotland. Allowing for improved security of supply and additional infrastructure in the future to help towards net zero | N/A | Knowledge sharing through emails, Microsoft Teams and face-to-face meetings. Technical reports and presentations with cost data and alternative solutions shared (SSEN Transmission) [RESTRICTED SHARING]. SSEN Distribution provided indicative costs data for distributions options (SSEN Distribution) [Restricted Sharing]. | N/A | Minimises social and environmental impact by building less across transmission and distribution, Enhances security of supply for consumers, Reduction in overall connection costs, Enables connection of renewable energy require to meet net zero in an efficient and economic manner Allows for future coordination with local council, communities and developers to ensure efficient and effective solutions are put forward to benefit the islands | Positive impact - Cost savings for network licensees and developers | Recommend ongoing co-ordination with SSEN Distribution and customers to progress with the recommended whole system solution | Potential to provide costs savings to all parties involved.
Related Action | SSEN/024 | SSEN Transmission | SSEN-D; local council, communities and developers | 22/23 | [13 empty] | Contribute to consultations and monitor their impact on the transmission system. | 2023-01-03 | New | SSEN/024
Co-ordination and cooperation activity | SSEN/025 | SSEN Transmission | SSEN-D; All DNOs and TO's, NGESO, ENA | 22/23 | DSO implementation plan and interactive road map | DSO implementation plan and interactive road map | Complete | 2026-12-22 |  | As part of the ENA Open Network Project there was an objective to create an implementation plan and interactive roadmap for stakeholders showing the DNOs transitioning to DSOs. This was fed into and agreed by all DNOs, ESO and TO with the ENA coordinating. This looked at all functions of the DSO including system operation, markets, coordination, planning, flexibility services etc. SSEN Transmission fed into this by providing evidence on what we are doing to support the implementation of DSO and fed into the work to ensure that the appropriate data exchange and coordination practices are in place to avoid any unintended consequences. | Open Networks: developing the smart grid - Energy Networks Association | Coordination with the ESO and DSO, system operation including restoration, network planning | https://www.energynetworks.org/creating-tomorrows-networks/open-networks/ | Our work in this area allowed coordination across the whole electricity system to ensure that the implementation of DSO functions were coordinated effectively and that any concerns or unintended consequences were avoided | Positive impact on stakeholder collaboration and ensuring the safe reliable and economic operation of the transmission network as the use and operation of the whole system changes | Work within the ENA has now been completed. This work is moving internally through collaborating regularly with SSEN Distribution on their progress of implementing DSO functions and services | Important to monitor and feed into any changes that may affect the safe, reliable and economic operation of the transmission network.
Related Action | SSEN/025 | SSEN Transmission | SSEN-D; All DNOs and TO's, NGESO, ENA | 22/23 | [13 empty] | Monitor the modifications made to the Grid Code. | 2023-01-04 | Business As Usual | SSEN/025
Co-ordination and cooperation activity | SSEN/026 | SSEN Transmission | SSEN-D; NGET; SPEN; Users, Ofgem,NGESO, ENA, Trade bodies | 22/23 | Market design arragements | Representing SSEN Transmission in market design arrangements prevalent across industry currently, ensuring whole system decarbonisation is considered when changing market arrangements. | Complete | Dec-22. 3/6/26 Strategic Planning confirmed this activity is complete | 2021-01-11 | Our evidence based work on this area monitors and tracks the effect that changing market signals, for those connecting to our network can have on the operation of both distribution and transmission networks. A key part of this work is also considering the impact on consumers and ensure society reaches net zero efficiently at least cost. | https://www.ssen-transmission.co.uk/information-centre/energy-markets-hub/ | Collaboration with industry bodies and wider stakeholders. | https://www.ssen-transmission.co.uk/information-centre/energy-markets-hub/ | Our work in this area has led us to be trusted source of information that stakeholders rely on. We have responded to key government consultations such as BEIS REMA consultation and Ofgem's Call for Input. | Positive impact on SSEN Transmission in particular around enhancing our stakeholder engagement. Our engagement on market reform has ensured that our future network planning is considered by key organisation stakeholders such as BEIS and Ofgem | Continue to contribute to key consultations that consider market arrangements and ensuring their impact on transmission is accounted for. | Grid charging, access and markets play a vital part of ensuring that we can deliver our business plan efficiently. It is important for us to continue to monitor change in this area and advocate where appropriate the requirements for our business, stakeholders and wider society.
Related Action | SSEN/026 | SSEN Transmission | SSEN-D; NGET; SPEN; Users, Ofgem,NGESO, ENA, Trade bodies | 22/23 | [13 empty] | Organise regular engagements with SSEN Distribution | 2023-01-06 | Business As Usual | SSEN/026
Co-ordination and cooperation activity | SSEN/027 | SSEN Transmission | SSEN-D; NGET; SPEN; Users, Ofgem, NGESO ENA, Trade bodies, Generators | 22/23 | Electricity Restoration Standard | Developing the markets and fundings arrangements for the Electricity Restoration Standard directed by BEIS in 2021. Representing SSEN Transmission on industry wide work group forums and code modifications to introduce the new standard effectively. | Complete | The latest update on this work as of March 2025 | 2022-01-01 | As part of the new standard, it is identifying new innovative ways to restoration, this includes utilising distributed restart and DG of restoration services. It is important that this is coordinated across the whole system to ensure effective data sharing and operational practices in place and the market and funding mechanisms for such services to avoid any unintended consequences | Electricity System Restoration Standard ¦ National Grid ESO | Mainly collaboration through work groups and delivery groups. The ESO shared their views and industry including SSEN Transmission provided input | Electricity System Restoration Standard ¦ National Grid ESO | Will allow more efficient, coordinated restoration of the system. Introducing new requirements that GB should be restored to 100% within 5 days and 60% within 24 hours | Positive impact as this ensures that the safety, reliability and economic operation of the transmission network is at the forefront of this work. | Work moved into Grid code modifications, continuing to monitor its progress. SMEs also providing input and support where appropriate | Important to monitor and feed into any changes that may affect the safe, reliable and economic operation of the transmission network.
Related Action | SSEN/027 | SSEN Transmission | SSEN-D; NGET; SPEN; Users, Ofgem, NGESO ENA, Trade bodies, Generators | 22/23 | [13 empty] | Progress with the recommended whole system option. This will involve SSEN Distribution applying for a new GSP at Eday. | 2023-01-05 | New | SSEN/027
Co-ordination and cooperation activity | SSEN/028 | SSEN Transmission | SSEN-D; local councils, communities and developers | 22/23 | Western Isles Whole System Study | Western Isles Whole System Study - working with SSEN Distribution to produce whole system report on infrastructure recommendations for the isles of Harris and Lewis. This involves discussing with SSEN Distribution the best method to integrate the Western Isles HVDC with the local network to provide demand security and secure connection of renewable generation to the grid. | Complete | May-23. 6/2/26 This work has been picked up by developments in the strategic planning space SSEP, CSNP and RESP. | 2023-01-22 | Enhanced demand security for local communities, environmental benefits due to reduction in use of backup diesel generation. | N/A | Data shared with SSEN Distribution on potential options, current and projected demand and generation on Western Isles. | N/A | Reduce dependance on diesel generation. Enhanced security of supply to communities and connection of renewable generation to the grid required to meet net zero. | Positive. SSEN Transmission develops network solutions that contribute to emissions reduction | Continued stakeholder engagement, energy scenario planning, and the assessment of options to determine the most efficient and economic whole system solution. | To provide security of supply to local communities and reduction in carbon emissions from using diesel generation in an optimal manner.
Related Action | SSEN/028 | SSEN Transmission | SSEN-D; local councils, communities and developers | 22/23 | [13 empty] | Engage with stakeholders and provide justifications for the investments. | 2023-01-12 | New | SSEN/028
Co-ordination and cooperation activity | SSEN/029 | SSEN Transmission | SSEN-D; local councils, communities and developers | 22/23 | Shetland Whole System Study | Shetland Whole System Study - Working with SSEN Distribution, developers and local authorities to develop a whole system network development plan on Shetland. | Complete | May-23. 3/3/26* This work has been completed and is superceded by the task 'Shetland on-island transmission network strategy' | 2022-12-22 | Potential cost savings on infrastructure costs, minimises environmental and social impact | N/A | Terms of references and work plans shared with SSEN Distribution [Restricted Sharing] | N/A | Minimises social and environmental impact by building less across transmission and distribution, Enhances security of supply for consumers, Reduction in overall connection costs, Enables connection of renewable energy require to meet net zero in an efficient and economic manner | Positive, cost savings across transmission and distribution | Recommend continuing whole system development plans for Shetland, identifying funding mechanisms for the project/s arising from this work, and engaging with Ofgem and stakeholders | Potential to provide costs savings to all parties involved.
Related Action | SSEN/029 | SSEN Transmission | SSEN-D; local councils, communities and developers | 22/23 | [13 empty] | Develop a whole system network for Shetland, identify funding mechanisms for the project/s arising from this work, engage with Ofgem and stakeholders | 2023-01-12 | Improving | SSEN/029
Co-ordination and cooperation activity | SSEN/030 | SSEN Transmission | SSEN-D; local councils | 22/23 | Dundee and Aberdeen City Network Development Strategies | Dundee and Aberdeen City Network Development Strategies - Worked with internal (System Planning, Asset Management, etc.) and external (SSEN Distribution) stakeholders to identify the load and non-load drivers for network investment in the Eastern cities of Dundee and Aberdeen. We have also undertaken stakeholder profiling and mapping exercise, as a first step, for each of the cities to identify key stakeholders and strategies of engagement and how the feedback will inform the project design | Complete | Feb-22. 4/3/26 Strategic Planning confirmed this activity can be closed | 2023-01-04 | A more holistic and cost-effective approach to network investment was achieved by simultaneously considering load and non-load drivers as well as the local plans for the cities, and by actively engaging the stakeholders. | N/A | Technical reports with identified load and non-load drivers, along with a stakeholder engagement strategy [Restricted Sharing]. | N/A | Increased consideration of a higher number of factors influencing network investment, potentially increasing the ability to make investment decisions that will result in a reduced cost to customers and consumers | Positive impact - Cost savings for network licensees. | Recommend ongoing co-ordination with SSEN Distribution and local councils to ensure that all drivers have been successfully identified. | Potential to provide costs savings to all parties involved.
Related Action | SSEN/030 | SSEN Transmission | SSEN-D; local councils | 22/23 | [13 empty] | Align all related projects on the Western Isles to determine the optimal whole system option(s). | 2023-01-09 | Improving | SSEN/030
Co-ordination and cooperation activity | SSEN/033 | SSEN Transmission | NGET; Icebreaker One, Southern Gas Networks, OLWG LTD, Mapstand LTD | 23/24 | REACT | REACT (Rapid Evaluation Areal Connection Tool) aims to create a geographical planning tool providing users with the ability to view electricity grid connection requests in real-time using an interactive visualisation map. Users will be able to identify the best possible locations to connect to the network, based on dynamic geospatial and network information, as well as a view of future demand and generation requests. This will streamline the connection process where limited pre-application information impacts formal applications. Optimising the location of demand and generation will increase the efficient use of existing assets and the effective roll-out of new infrastructure. | Not taken forward | Feb-25 - Project didn't get funding for Beta phased so is now an NIA project (purely SSEN). | 2023-01-11 | REACT is addressing the challenges in the connection request process by providing an early dynamic view of all forecasted connection requests to highlight optimal locations and other key parameters. The main focus is the H2 use case explored in Discovery | https://smarter.energynetworks.org/projects/ukri10058535/ https://smarter.energynetworks.org/projects/ukri10079052/ | [Widely shared] Reports published on the ENA portal | https://smarter.energynetworks.org/projects/ukri10058535/ | REACT will deliver the following net benefits to consumers: Financial - Cost savings for users of network services Significant interest to connect hydrogen electrolysis sites to the SSEN-T Network has resulted in multi-million-pound connection offers being made to developers due to the capacity requested and limited availability on the network. These requests would require costly reinforcement of the network, which would slow down the energy transition and increase consumers bills. Offering the tool to developers before they submit requests could deliver large savings by providing alternative locations to site their project on the existing network with more capacity. REACT will also save time and resource by eliminating the need for developer pre-application calls by providing them with all the information they need prior to the application. These calls cost approximately £6.3Kpa and will increase as connection requests rise. We&#39;ll review the savings on project development, pre-application costs and Transmission Network Use of System charges throughout the Project. Environmental - Direct CO2 savings p.a against a business-as-usual counterfactual REACT will reduce the carbon emissions of building new infrastructure which would be required for the increase in connection requests. By utilising the existing network where possible, REACT will deliver direct environmental benefits. Environmental - Indirect CO2 savings p.a against a BaU counterfactual Carbon reductions will be investigated to identify the amount saved through reducing the delivery delays of hydrogen projects, while taking into consideration the ESO's and SSEN-T's North of Scotland future energy scenarios. | Improved systems planning and line of site of system needs. | Completion of Alpha Phase and submission of a Beta Application. | The project had a live demonstrator and we are now looking to move to BAU.
Related Action | SSEN/033 | SSEN Transmission | NGET; Icebreaker One, Southern Gas Networks, OLWG LTD, Mapstand LTD | 23/24 | [13 empty] | Incorporate published outputs into BaU HND and HND FUE Infrastructure delivery forums - leading to identification of the final preferred design for the offshore systems. Detailed network design of both the offshore and onshore system (following on from the recommendations of the HND FUE / tCSNP2 publication), developing our projects towards construction. | 2023-02-06 | Improving; Business as Usual | SSEN/033
Co-ordination and cooperation activity | SSEN/034 | SSEN Transmission | NGESO, The Carbon Trust | 23/24 | SIF Project BluePrint | SIF Project BluePrint will develop solutions that facilitate the connection of new low-carbon energy to already-constrained areas of the GB network (such as northern Scotland in SSEN-T's network area) as quickly as possible, and to maximise energy export once connected by avoiding constraint-driven curtailment. | Not taken forward | Feb-25 - Project not taken forward | 2023-01-11 | Blueprint addresses the &#39;Whole system planning for faster asset rollout&#39; SIF Challenge. Discovery brings together TOs, ESO, and OWF developers to develop an improved, collaborative understanding of the key risks of developing behind constraint. This will improve whole systems cross-industry planning. It will also improve understanding of how innovative solutions can accelerate the development of the HND network and optimise the use of the existing network, and hence accelerate OWF rollout in currently constrained areas. | N/A | [Widely shared] UKRI Application for funding | N/A | The project will understand how novel, collaborative approaches to data and commercial arrangements can be used to deliver the HND and mitigate the risks in its delivery, fully aligned with SIF&#39;s Innovation Challenge focus Theme 2. The project is also relevant to Theme 3, as novel, collaborative, flexible arrangements between demand and generation will be considered as a possible solution for mitigating the risks in delivering the HND. Linked to Theme 4, hydrogen generation will be considered as a possible solution. | Delivery of whole system thinking to the business. | Start delivery of the Discovery Phase project. | Project has confirmed funding from the UKRI
Related Action | SSEN/034 | SSEN Transmission | NGESO, The Carbon Trust | 23/24 | [13 empty] | Feb 2025 - Out of discovery phase - now in Alpha phase. Looking to prepare an application for Beta phase. 2024 - Initiation of the Discovery Phase project and signing of the collaboration agreements. | 2024-01-03 | Improving | SSEN/034
Co-ordination and cooperation activity | SSEN/035 | SSEN Transmission | NGET; NGESO,University of Strathclyde,Met Office, Gilytics, Energy Line | 23/24 | REVISE | REVISE is primarily focused on revisiting the current methodology for assigning overhead line ratings. The calculation process uses historical environmental data captured in the 1980s that is applied uniformly across the UK disregarding local/regional climate variations. The existing transmission network is increasingly constrained by system capacity limits exacerbated by rapidly increasing renewable integration. Improving understanding of line ratings, using latest generation high-resolution weather topographic data combined with the latest techniques for system modelling, will allow for improved targeted investment to ensure we meet demand for the connection of new renewables to the network, securing a safer and greener future. | In progress | Feb-25. The Revise project has been funded for BETA phase - with a start date of March 2026 | 2023-01-11 | Provides additional capacity from existing assets to accelerate the connection of new assets, generators, services. | N/A | [Widely shared] Summary of UKRI application for funding. | https://smarter.energynetworks.org/projects/ukri10058535/ | REVISE offers the following: (1) Alleviating the constraint on renewable generation reduces the partial reliance on gas/diesel generation used to offset the difference. (2) Circuit rating achieved with no physical works and the associated embedded carbon involved. (3) May enable smaller renewable schemes to connect without the need to wait for further infrastructure works, helping to progress the connection queue. (4) May remove the need to upgrade/replace circuits following a connection request | Provides additional capacity and speeds up connection times. | Delivery of the Discovery Phase projects, and recommendation for progress. | The Discovery Phase is funded.
Related Action | SSEN/035 | SSEN Transmission | NGET; NGESO,University of Strathclyde,Met Office, Gilytics, Energy Line | 23/24 | [13 empty] | Start of the delivery of Discovery Phase project. Feb 2025 - Project cancelled following Discovery phase. | 2024-01-03 | Mature | SSEN/035
Co-ordination and cooperation activity | SSEN/036 | SSEN Transmission | NGET; SPT; NGESO | 22/23 | HND, HND FUE and tCSNP2 Process | HND, HND FUE and tCSNP2 process. The Holistic Network Design (HND) is coordinated by the ESO and involves all three TO's in Great Britain. The HND process provided a set of recommendations to facilitate the connection of 50GW of offshore wind by 2030, taking account of four Network Design Objectives: economic and efficient, deliverable and operable, environmental impact and community impact. The HND Follow Up Exercise (FUE) is providing a follow-up recommendation for the offshore system design for the connection of further offshore wind (i.e. all ScotWind) beyond 2030, and the tCSNP2 process is providing the corresponding onshore reinforcement strategy (similar to the previous NOA process). The HND, HND FUE and tCSNP2 processes have required strong cooperation and collaboration with the ESO and other TO's (NGET and SPEN). Further, detailed network design of both the HND offshore East Coast coordinated network and HND FUE offshore coordinated network has begun (requring strong cooperation and collaboration from offshore wind farm developers as well as NGET and the ESO). | Complete | Mar-24. 4/3/26 Complete, progress to tCSNP2R | 2022-09-22 | The HND FUE and tCSNP2 processes will further support the Government's previously stated government targets for offshore wind and net zero; facilitating an economic, efficient, operable, and coordinated National Electricity Transmission System (NETS) (including offshore and associated onshore assets required to connect in scope projects). The detailed design activities for both the HND and HND FUE coordinated offshore systems are critical to realise the connection of significant offshore wind and minimise environmental/community impact onshore (fullfilling the aims of the HND and HND FUE processes). | N/A | Mainly collaboration through work groups and delivery groups. [Some restricted and some widely shared] [External] Published ESO reports | https://www.nationalgrideso.com/document/270851/download tCSNP2 publication (which covers HND FUE) is due mid-March | The HND FUE will identify the most efficient, economic and effective approach to connect over 50GW of offshore wind across Great Britain - minimising environmental and community impact. | This will ensure that SSENT and the other TO&#39;s within Great Britain can accommodate offshore wind connections in an efficient, economic and effective way. | HND FUE / tCSNP2 publication by ESO is expected in March 2024. Detailed network design of the offshore and onshore strategic network reinforcements - requiring strong cooperation and collaboration with NGET, the ESO, and offshore windfarm developers. | This work will help inform connection of offshore wind critical to delivering Net Zero.
Related Action | SSEN/036 | SSEN Transmission | NGET; SPT; NGESO | 22/23 | [13 empty] | Agreement on the Beta Application for funding with the project partners Feb 2025 - Didn't get funding for Beta phase, now an NIA (purely SSEN) project. | 2024-07-31 | Mature | SSEN/036
Co-ordination and cooperation activity | SSEN/037 | SSEN Transmission | NGET; The University of Dundee | 23/24 | OHL Foundation Uplift Project | Work on the OHL Foundation uplift project to investigate improved foundation designs. Through collaboration with NGET, University of Dundee and University of Bristol the new foundation design will improve efficiency for project timeframes as well as cost savings. | Complete | Feb-26 Project completed and deliverables received / reviewed. | 2022-11-30 | The new design will be used throughout the industry to reduce the time taken to build foundations as well as the amount of material needed for foundation builds | https://smarter.energynetworks.org/projects/nia_shet_0039/ | [Widely shared] Project reports and lessons learned are shared with the University to allow them to design the new foundation. The new models and designs are shared with the partners to allow for corroboration. | N/A | This activity will have a positive impact on the whole system in allowing for more cost effective, quicker construction of the networks allowing more renewable to connect to the network quicker and for less cost. This will benefit consumers in the long term. | The impact on SHET will be positive in that it is expected that the new foundation design will allow for quicker and cheaper construction. | Project to be completed and results assessed by NGET and SHET. Further work may involve additional testing of larger structures. | Project has the potential to reduce the time taken to construct overhead line circuits as well as reduce the carbon footprint.
Related Action | SSEN/037 | SSEN Transmission | NGET; The University of Dundee | 23/24 | [13 empty] | Feb 2025 update - Project was cancelled after Beta Phase. 2024 update - Conclude Beta Phase 1 of project and disseminate knowledge. | 2024-01-09 | Mature | SSEN/037
Co-ordination and cooperation activity | SSEN/038 | SSEN Transmission | National HVDC Centre, NGESO, The University of Edinburgh, The Carbon Trust, Super Grid Institute | 23/24 | Network-DC | Network-DC The UK government has set targets to increase offshore wind to 50GW by 2030. The method for connecting offshore wind farms to the grid is to connect each wind farm to an alternating current (AC) converter station with an AC circuit breaker between the converter station and the rest of the onshore AC network, to protect. Feb 26 - project now finished and activity marked complete the electricity grid from faults on the offshore direct current (DC) network. This method results in stand-alone assets connected directly to the transmission grid, increasing the total number of required AC converter stations. As the number of wind farms increases, the number of AC convertor stations increases. Without innovative solutions, the growing network of High Voltage Direct Current (HVDC) connections around GB will be less flexible and responsive, resulting in higher assets and system operating costs. DC circuit breakers (DCCBs) are more than likely to be required to deliver a multi- terminal HVDC hub serving multiple offshore wind generation sites, GB transmission links, and international interconnections. Network-DC will investigate and demonstrate the use of DCCB, an innovative technology untested in the UK and European markets. DCCBs will allow us to bring multiple wind farms into a DC system, containing the impact of any single failure safely and securely. This Project brings together international partners to accelerate the readiness of DCCBs for installation into the design of the UK HVDC Network, and outline a clear pathway for the installation of the UK's first DCCB. | Complete | Feb 2025 - still in progress | 2022-01-09 | A DCCB hub will reduce the need for AC infrastructure and effectively isolate faults in offshore network components. This project will build confidence in DCCBs allowing utilisation across the network. Enables more economic connection of offshore wind to UK mainland grid. | https://smarter.energynetworks.org/projects/10020383/ https://smarter.energynetworks.org/projects/10036946/ https://smarter.energynetworks.org/projects/10067854/ | [Widely shared] ENA Public website | N/A | Reduces the total amount of infrastructure. | Build expertise in design and commissioning of DC-Circuit breakers. Reduces future connection time. Simplify the operation of the network. | Progress BETA phase work with recommendations for specification of DC Breaker on UK network. | BETA phase is fully funded and is progressing.
Related Action | SSEN/038 | SSEN Transmission | National HVDC Centre, NGESO, The University of Edinburgh, The Carbon Trust, Super Grid Institute | 23/24 | [13 empty] | Continue to deliver the Beta phase work packages. | 2023-01-11 | Improving | SSEN/038
Co-ordination and cooperation activity | SSEN/039 | SSEN Transmission | National HVDC Centre, NGESO, University of Strathclyde, The Carbon Trust | 23/24 | INCENTIVE | INCENTIVE will investigate and demonstrate how offshore wind farms (OWF) can provide inertia to the onshore networks. This will provide grid stability and reliability at a lower cost, and reduce the need for additional infrastructure by co developing and co-locating inertia services with OWFs. OWFs providing inertia to the onshore network is not an incremental innovation, but a step-change in thinking that could be replicated globally. INCENTIVE will investigate OWFs with: 1. STATCOM with supercapacitor energy storage and grid forming converter. 2. Battery energy storage system (BESS) with overrated grid forming converter. 3. Synchronous condenser with flywheel. These solutions have never been trialled in conjunction with an offshore wind farm before making this a first-of-its-kind project. The Project brings together OWF developers, technology suppliers, NGESO, and Ofgem, to help build a cross-industry understanding of the INCENTIVE solutions. | Not taken forward | Feb 2025 - Project cancelled after Beta phase. | 2022-01-03 | The energy contained in generators at power stations and industrial facilities provides inertia as they rotate at the same frequency as the electricity grid. Inertia in the GB electricity network is falling. Without novel solutions, adding additional renewable generation capacity will become increasingly challenging and could increase the operating cost of the GB network system and consumer bills. Historically, renewable generators have not treated system inertia as their problem as it has been high. However, we are already seeing renewable generation curtailed due to low system inertia. | https://smarter.energynetworks.org/projects/10067856/ https://smarter.energynetworks.org/projects/10037143/ https://smarter.energynetworks.org/projects/10024879/ | [Widely shared] ENA Public website | N/A | INCENTIVE will deliver benefits over and above those achievable through existing programmes (i.e. The Stability Pathfinder). These include: (1) Introduction of design alterations to requisite or already-planned assets to provide inertia. (2) Capturing cost savings by building inertia provision alongside building OWFs. For example, sharing network, access, and planning considerations. (3) Accelerating the connection of renewable assets by proactively addressing inertia at the outset. (4) Driving down market prices by creating a liquid market for inertia services | Benefits consumer and ancillary service providers, impact on SSEN-T is largely neutral as SSEN_T cannot take part in the ancillary services market. | Completion of the Beta Phase 1 and approval to move to Beta Phase 2. | Completion of Beta Phase 1 shows a positive outcome in terms of benefits.
Related Action | SSEN/039 | SSEN Transmission | National HVDC Centre, NGESO, University of Strathclyde, The Carbon Trust | 23/24 | [13 empty] | Coordinate further testing and introduction into BaU | 2024-03-30 | Mature | SSEN/039
Coordination and cooperation activity | SSEN/040 | SSEN Transmission | Dundee City Council | 23/24 | Dundee City Strategy | Having regular meetings with the Climate, Economic and Planning teams in Dundee City Council to introduce SSEN-T and discuss the Dundee City Strategy, areas for collaboration and input from their LAEP and LHESS | Closed | Latest update as of 01/02/2024. No longer on Whole System app. Activity and Acrtion Closed, included on the register for historic context. | 2023-08-01 | Regular quarterly meetings with Dundee City Council is creating a good relationship with the council and provides a forum to update on the progress of their LAEP and LHESS which can feed into the city strategy. It also helps to flag any issues or risks we need to be aware and explores areas of opportunity which may feed in to the strategy. | None | An overview of Dundee City Network Development Strategy developed by SSEN-T. [Restricted Sharing] | N/A | Effective stakeholder engagement with local authorities, SSEN-D and SSEN-T to increase awareness of strategy and approach to create a positive working relationship | Creating positive relationships with stakeholders | Continued engagement with the next meeting taking place on 23 April 2024 | Important to maintain the relationship and continue with the effective engagement that has a value to all parties.
Related Action | SSEN/040 | SSEN Transmission | Dundee City Council | 23/24 | [13 empty] | Next meeting organised for 23 April 2024 | 2024-04-23 | Mature, Closed | SSEN/040
Co-ordination and cooperation activity | SSEN/041 | SSEN Transmission | SHEPD, NGESO | 23/24 | Centralised Flexible Connections Solution | A whole system solution to deploy a centralised flexible connections solution to provide quicker network access to renewable generation in a manner that minimises costs to the GB consumer and removes barrier to entry for small scale renewable generation | In progress | 2026-02-24 | 2024-08-01 | Quicker network access to renewable generation in a manner that minimises costs to the GB consumer, removes barrier to entry for small scale renewable generation and accelerating our contribution to net zero. | N/A | [Restricted sharing] Connection application information including customer data, High level options being considered | N/A | This is ongoing but is expected to be positive as it will provide quicker network access to renewable generation in a manner that minimises costs to the GB consumer, removes barrier to entry for small scale renewable generation and accelerates our contribution to net zero | This is ongoing but it is expected to be positive as it will provide quicker and increased network access to renewable generation and accelerate our contribution to net zero | Define functional and nonfunctional requirements and get agreement with the ESO to deploy the scheme in line with STCP 26.1 – Active Network Management. | This will provide quicker network access to renewable generation in a manner that minimises costs to the GB consumer, removes barrier to entry for small scale renewable generation and accelerates our contribution to net zero
Related Action | SSEN/041 | SSEN Transmission | SHEPD, NGESO | 23/24 | [13 empty] | Information fed to sections of business involved in strategic planning. | 2024-01-04 | Mature | SSEN/041
Co-ordination and cooperation activity | SSEN/042 | SSEN Transmission | SHEPD, NGESO, University of Strathclyde, NSTA/SIC/Statkraft/Offshore developers | 23/24 | Shetland Strategy | As part of Shetland strategy, planning the future transmission network on Shetland, a close engagement with SHEPD as the distribution network owner and operator on Shetland was necessary. At the beginning of the project we reached out to SHEPD to understand their future plans in terms of GSPs and their corresponding capacities and how this can fit into the whole system solution for Shetland. This has helped assigning potential distribution customers to the closest potential GSP to help optimise the 33kV network. Then, we engaged with SHEPD to get their distribution energy profiles, those have been considered along the transmission energy profiles to assess the operation of the system throughout one typical year of operation. We have also worked closely with SHEPD on their fault ride through solution and how the future transmission strategy impacts on it. We have regular workshops with SHEPD to review the proposed network options and prepare relevant maps to show the paths that both transmission and distribution networks will take considering the planned transmission substations and customer connections offered by SHEPD | Complete | The latest update on this work as of March 2025 | 2023-06-13 | The whole system solution is to help optimise the required system operability assets, identify and reduce or suppress potential costs of rebuild, and assess opportunities for common use of land to build electrical assets for the whole system solution namely substations. |  | [Restricted sharing] Minutes of the last two meeting held with SHEPD and also a link to the distribution profiles shared. Files shared by SHEPD as part of the whole system solution. | N/A | Overall positive. However, there are some challenges related to changing projects impacting contracted customers either from SSEN Transmission or SHEPD side. | Positive. This enables us to plan an economic and efficient whole system solution in a coordinated manner. | Continue work to achieve the most from the whole system solution | Work in progress, not yet concluded.
Related Action | SSEN/042 | SSEN Transmission | SHEPD, NGESO, University of Strathclyde, NSTA/SIC/Statkraft/Offshore developers | 23/24 | [13 empty] | GB wide publication by ESO of the Pathway to 2030 and the Beyond 2030 reports with investment recommendations for both onshore & offshore network design choices. Feb 2025 update: GB wide publication by ESO of the Pathway to 2030 and the Beyond 2030 reports with investment recommendations for both onshore & offshore network design choices. SSENT is working towards delivery and development of schemes which had received appropriate recommendations as part of Pathway to 2030 and Beyond 2030 reports. SSENT Planning and Regulations teams are engaging with NESO and OFGEM to progress on tCSNP2 outputs. | 2024-03-20 | Improving | SSEN/042
Co-ordination and cooperation activity | SSEN/043 | SSEN Transmission | NGESO, SPEN, NGET, National HVDC Centre | 23/24 | HND, HNDFUE & tCSNP2 | 1) HND: The Network Planning team is extensively working with the ESO, NGET, Offshore Developers and the HVDC centre to identify an economic, efficient and deliverable solution as per of the HND offshore coordinated network. 2) HNDFUE: As part of next step to HND exercise over the 2023-24 period , we extensively worked with the ESO, NGET, SPEN and others to identify the most suitable offshore coordinated network that will help us to deliver the network to facilitate Net Zero targets by 2035. 3) tCSNP2: The Network Planning team collaboratively worked with the ESO, NGET, Developers and HVDC centre to identify economic, efficient and deliverable onshore network reinforcement options to support HNDFUE offshore coordinated network that will enable us to meet our commitments to achieve decarbonisation of Grid. | Complete | Updated Feb 2025: 1) HND: The Network Planning team is extensively working with the NESO, NGET and Offshore Developers to identify an economic, efficient and deliverable solution as per of the HND offshore coordinated network. The work is ongoing. 2) HNDFUE: As part of next step to HND exercise over the 2023-24 period , we expansively worked with the NESO, NGET, SPEN and others to identify the most suitable offshore coordinated network that will help us to deliver the network to facilitate Net Zero targets by 2035. There is extensive engagement with developers and NESO through Detail Network Design clusters to progress on finalise deliverable offshore network design. The work is ongoing. 3) tCSNP2: The Network Planning team collaboratively worked with the NESO, NGET and OFGEM to identify economic, efficient and deliverable onshore network reinforcement options to support HNDFUE offshore coordinated network that will enable us to meet our commitments to achieve decarbonisation of Grid. This output of this process was confirmed by NESO via Beyond 2030 report which was published in March 2024. 4/3/26 Complete and moved to tCSNP2R activity | 2023-09-01 | All the activities listed above needs collaborative working with all the players from GB energy industry including but not limited to OFGEM, ESO, NGET, SPEN etc | N/A | [Restricted sharing] | N/A | These are critical activities which enable the ESO to identify economic and efficient options for development onshore and offshore to support the development of a coordinated GB network. | Deliver the most economical, efficient and deliverable network with due regard to environmental and societal considerations. | N/A | N/A
Related Action | SSEN/043 | SSEN Transmission | NGESO, SPEN, NGET, National HVDC Centre | 23/24 | [13 empty] | Continue coordination with stakeholders. This feeds directly into the Needs Case for the Shetland Whole System solution for submission to Ofgem during 2024 2025 update: an EJP was submitted to Ofgem as part of T3. | 2024-03-29 | Business As Usual | SSEN/043
Co-ordination and cooperation activity | SSEN/044 | SSEN Transmission | SSEN-D; ES Catapult, Regen | 23/24 | RESP Study | We are undertaking a study on Regional Energy System Plans (RESP) relating to our work on system planning and how strategic area plans might impact the network. We have had discussions with SSEN Distribution, ES Catapult and Regen to provided greater understanding of the current status of RESPS and local area planning. | Complete | The latest update on this activity as of March 2025 | 2024-01-03 | Strategic planning of the network such as RESPs includes considering aspects on connections, planning, charging, markets. | N/A | [Some restricted and some widely shared] Project still gathering knowledge based information. | N/A | Positive - provides greater insight into how future regional and strategic plans might be aligned. | Positive- provides greater insight into how future regional and strategic plans might be aligned. | Ongoing engagement; write up report, disseminate to appropriate areas of the business | Initial investigations have already proved inciteful and raised further questions.
Related Action | SSEN/044 | SSEN Transmission | SSEN-D; ES Catapult, Regen | 23/24 | [13 empty] | Define functional and nonfunctional requirements and get agreement with the ESO to deploy the scheme. | 2024-09-30 | New | SSEN/044
Co-ordination and cooperation activity | SSEN/045 | SSEN Transmission | SPEN; NGET; NGESO | 23/24 | Electricity Ten Year Statement (ETYS) | Electricity Ten Year Statement work to develop GB network models for future years, and providing technical data as required for publishing in the report. | Complete | 2026-03-24 | 2023-01-09 | Working with the other TOs across GB, as well as the ESO, to develop whole GB network transmission models for current and future years. | https://www.nationalgrideso.com/research-and-publications/electricity-ten-year-statement-etys | Data shared is network modelling data. We share our network models (PSSE) and then share modelling data for publishing as part of the ETYS. Some restricted and some widely shared | N/A | Coordinated work with other TOs and the ESO to develop whole GB transmission network models for all TOs and the ESO. Models are used in the system planning of the GB grid. | This results in us having updated Transmission Network master GB models for undertaking all system analysis studies. This enables the planning of the network to be undertaken at a GB level, ensuring coordination. | This is an annual process and will continue next year (ETYS 2024 has kicked off already). | This is a licence obligation to continue
Related Action | SSEN/045 | SSEN Transmission | SPEN; NGET; NGESO | 23/24 | [13 empty] | There are follow-on activities across trial sites. The process has been accepted within the company. | 2023-12-15 | New | SSEN/045
Co-ordination and cooperation activity | SSEN/046 | SSEN Transmission | SHEPD; NGESO | 23/24 | Connections Reform | Work undertaken to consider how connections reform will align with requirements of a more strategically planned networks and recommend any changes as a result | In progress | March/ April 2026 Update - Activity will be revisited through Gate 2 / Whole Queue. A derogations paper was submitted to Ofgem as part of T3. It was noted that previous queries may have implied an attempt to bypass derogation routes; wording should clarify that this was not the intent, only that a potential future delegation might be required depending on G2tWQ outcomes. | 2023-01-02 | Requires input and collaboration across T/ D and T/ESO | N/A | No specific data exchanged other than worked examples of the connections process under TMO4 and an explanation of the TO's role in a more strategically planned network. Widely shared | N/A | Positive - a proposed solution will provide direction and more certainty towards developers in the queue | Positive - provides better alignment between SSEP and connections process | Seek industry endorsement and move to code modification to implement solution | This is essential if we are to realise the benefits of both strategic network planning and a reformed connections process
Related Action | SSEN/046 | SSEN Transmission | SHEPD; NGESO | 23/24 | [13 empty] | Weekly calls and system planning touchpoints. | 2025-04-01 | Business As Usual | SSEN/046
Related Action | SSEN/046 | SSEN Transmission | SHEPD; NGESO | 23/24 | [13 empty] | Engagement via ENA (March 2024 noted in the register). | 2025-04-01 | Improving | SSEN/046
Related Action | SSEN/046 | SSEN Transmission | SHEPD; NGESO | 23/24 | [13 empty] | Cross‑transmission and distribution engagement. | 2025-04-01 | Business As Usual | SSEN/046
Related Action | SSEN/046 | SSEN Transmission | SHEPD; NGESO | 23/24 | [13 empty] | Further co-ordination activity to assess trial status | 2024-04-19 | New | SSEN/046
Co-ordination and cooperation activity | SSEN/047 | SSEN Transmission | SHEPD; NGESO | 23/24 | T/D Limits Methodology | Work undertaken to provide methodology for setting T/D limits at GSPs. Currently Some processes already in place in England. | Complete | 2026-12-23 | 2023-01-04 | Involved co-ordination across T & D in setting methodologies for dealing with setting capacity. | https://www.ssen.co.uk/our-services/tools-and-maps/eoi-form/ | Data exchanged between T and D was Mvar of capacity available at selected GSP's via Appendix G. Some restricted and some widely shared | N/A | Positive - T + D have worked together on the dealing with limits at T/D boundary to enable more generation to connect within the scope of the work | Positive - Greater Liaison with D counterparts. | The process has already been rolled out to trial sites. | The project aimed to trial the process once the details had been agreed.
Related Action | SSEN/047 | SSEN Transmission | SHEPD; NGESO | 23/24 | [13 empty] | Progress next ETYS cycle starting with model builds. Network modelling work feeds directly into the production of the ETYS as well as the tCSNP/NOA | 2024-08-01 | Business As Usual | SSEN/047
Co-ordination and cooperation activity | SSEN/048 | SSEN Transmission | SPEN; NGET; NGESO; NESO; SPT | 23/24 | Joint Planning Committee Modelling Group | Joint Planning Committee Modelling Group. Quarterly meeting with TOs and ESO across GB to discuss network modelling activities and issues | In progress | March 26 update - "Agenda is still pretty standard with a focus on ongoing coordination between TOs and NESO on network modelling including the GB Planning Model." Martin Paul (key contact). Quarterley sub-group meeting as part of wider JPC | 2023-01-01 | Work with other TOs and the ESO to resolve any issues on network modelling or discuss other modelling activities | N/A | This is a face to face meeting to discuss issues/concerns regarding network modelling and this sub group reports to the overall JPC group. Restricted sharing | N/A | Enables TOs and ESO to review modelling assumptions or address issues with regards to network modelling with a level of consistency across parties. | Allows us to raise modelling issues and engage with other parties in GB, to ensure effective coordination of network plans. | Continue to meet as a sub group to address ongoing and new issues | This is necessary to continue improvement on the modelling of the GB network.
Related Action | SSEN/048 | SSEN Transmission | SPEN; NGET; NGESO; NESO; SPT | 23/24 | [13 empty] | Actions continue and any recommendations or processes that come out of it will be actioned upon as required. Outcomes relate to all system modelling work on the GB network. | 2023-01-01 | Business As Usual | SSEN/048
Co-ordination and cooperation activity | SSEN/049 | SSEN Transmission | SSEN-T; SSEN-D; SHEPD | 23/24 | HOWSUM Steering Group | The Hebrides and Orkney Whole System Uncertainty Mechanism (HOWSUM) Steering Group is comprised of both SSEN Distribution and Transmission colleagues to arrive at the optimal whole system solution accounting for future demand and generation, subsea cable asset condition, island resilience and decarbonisation | Complete | Mar-24. *Take closing update from Distribution. 6/2/26. 4/3/26 Complete, part of the Strategic Alignment activities. | 2022-01-12 | This group establishes working relationships between SSEN Transmission and SHEPD. THIs also supports consistent engagement with local councils and communities. | N/A | Knowledge sharing through emails, Microsoft Teams and face-to-face meetings |  | Allows for future coordination with local council, communities and developers to ensure efficient and effective solutions are put forward to benefit the islands | Positive impact with the population of the islands by building better relationships to tackle future problems, improve network security of supply and decarbonise the islands. | Continued collaboration to progress reports. HOWSUM 2024 has been submitted with costs to follow. Work towards HOWSUM 2025 submission, exploring T&D options and determining the most efficient and economic solution to be progressed. | Collaboration will be crucial to deliver the efficient and economic solutions while accounting for the or future demand and generation, subsea cable asset condition, island resilience and decarbonisation
Related Action | SSEN/049 | SSEN Transmission | SSEN-T; SSEN-D; SHEPD | 23/24 | [13 empty] | Continue to engage with Scottish Enterprise, Developers and SHEPD to support future requests from similar technologies | 2024-01-04 | Business As Usual | SSEN/049
Co-ordination and cooperation activity | SSEN/050 | SSEN Transmission | SHEPD | 23/24 | Shetland Strategy | Fortnightly meetings on the Shetland Strategy which includes involvement from SHEPD on what we at Transmission are looking to progress, and what information we need from SHEPD/what impact this may have on SHEPD infrastructure and current contracted customers. | Complete | Latest update as of Feb 2025 | 2023-01-06 | We are taking a holistic view of the current distribution network on Shetland, and how the newly created transmission infrastructure interacts. | N/A | N/A | N/A | Positive - will provide a more holistic view | Positive - shows we are thinking out the box and shows our understanding that dealings on Shetland are very different to the mainland | Preferred outcome of the strategy to be finalised and communicated to contracted customers, Ofgem, ESO and then wider through a webinar for various stakeholders. Needs cases will need to be submitted to Ofgem on the back of this. | This is the view across the internal business of next steps/following procedures.
Related Action | SSEN/050 | SSEN Transmission | SHEPD | 23/24 | [13 empty] | Stakeholder webinar to be held in June which will ultimately be used to support Ofgem submissions later in the ear. 2025 update: All stakeholders have been made aware of strategy outputs and impacts | 2024-01-06 | Business As Usual | SSEN/050
Co-ordination and cooperation activity | SSEN/051 | SSEN Transmission | SHEPD;Scottish Enterprise; | 23/24 | Data Demand Centres | SSEN Transmission were invited to attend a call with Scottish Enterprise to discuss the connection of data demand centres throughout our network area. With significant wind resource and pipeline of contracted Scot Wind generation, Scotland has rightly been chosen as a destination where demand is generally seen as a positive. The challenges to connection are around bay availability and space within substation, rather than network reinforcements to cater for the demand. The call was followed up with an introductory face-to-face meeting with Scottish Enterprise and one of their clients, who were looking to build out a data demand centre somewhere in Scotland. Scottish Enterprise had identified 10-15 sites around Scotland that they believed could be used for these centres, however, a grid connection did not make up part of their thinking, so most of the sites earmarked, would prove very challenging to connect to the grid. There was one site identified at Edzell Woods, which we discussed with the developer as being the most logical from a grid perspective. We explained that any Transmission connection would likely have a 6-7 year programme to build out from our substation to their site, as well as limitations on where we could physically connect their project, due to a shortage of connection bays. At this point, we introduced the possibility of their initial phase 1 50MW demand connecting via the distribution network and when their ramp up to circa 500MW was required, Transmission infrastructure would potentially be ready for them. SHEPD attended a call to discuss some of the GSP's nearby, discussing headroom left on the transformers, as well as how the physical connection would look. The conversations to date have been very valuable and have given the customer the most efficient way to connect their scheme, in the most timely manner for them. We are now awaiting a potential grid application for the data demand centre. This co-ordination between T and D could get the customer connected earlier to the system and bring 10's of Millions of pounds investment to the Scottish economy. | Complete | Latest update Feb 2025 | 2023-01-07 | SSEN Transmission and Distribution working collaboratively to find an optimal solution for the connection of new technology to the GB Network. | N/A | N/A | N/A | Positive - Earlier connection to the grid and large investment in local economy. | Positive reputation following co-ordinated approach, finding solutions on how to connect the customer earlier by involving SHEPD colleagues. | Waiting for grid connection application to formally move the project forward. | We have provided all information asked of us. The decision is now with the developer to submit an application, so we can work on issuing a connection offer with anticipated connection dates and associated costs.
Related Action | SSEN/051 | SSEN Transmission | SHEPD;Scottish Enterprise; | 23/24 | [13 empty] | Continued engagement with SHEPD to suppot Transmission input on the 2025 HOWSUM submission. This will include attending the steering group and Director level workshop | 2024-01-04 | Business As Usual | SSEN/051
Co-ordination and cooperation activity | SSEN/052 | SSEN Transmission | SSEN-D; SHEPD | 23/24 | Using a whole system approach to support RIIO T3 submissions. | Using a whole system approach to support RIIO T3 submissions. 1. Dundee creation of regional development strategy which is driven by the asset life of a number of GSP locations across the Dundee area. The strategy seeks to address the drivers while considering other load, non-load and distribution requirements. 2. East Coast 132kV network- A similar approach has been taken to strategically plan that part of the transmission network recognising asset condition, customer connection and GSP interactions. | In Progress | 2026-03-24 | 2022-01-02 | Both activities rely on a coordinated approach both across Transmission (load and non-load) and with SHEPD to develop a solution to future proof the network with a coordinated, economic and efficient design. | N/A | emails, Teams meetings, workshop | N/A | This has a positive impact on whole system by continuing to demonstrate our ability to coordinate internally and externally and develop a solution to future proof the network aligning with growth in generation to help meet net zero targets | Assure alignment and no-regret in development of solution | Engineering Justification Papers will be produced for both Dundee and East Coast strategies which will then be submitted with the T3 business plan | The primary driver for both EJP's will be asset health and must be accounted for in our next business plan submission ensuring that we deliver a solution which meets our future load requirements
Related Action | SSEN/052 | SSEN Transmission | SSEN-D; SHEPD | 23/24 | [13 empty] | Submission of EJP's for RIIO T3 | 2024-01-04 | Business As Usual | SSEN/052
Co-ordination and cooperation activity | SSEN/053 | SSEN Transmission | NESO | 24/25 | SHEPD Engagement on Nairn GSP | Recurring monthly meetings held with SHEPD, arranged by the project Customer Relationship Manager to ensure the customer (SHEPD) remain up to date with the project progress. 06/02/2026 - A new offer has been issued to SHEPD. The connection date has been reissued as Oct 2032 due to the requirement to acheive the original scope on a new parcel of land given the constraints around the GSP. A phased connection has been offered to enable the battery to connect in 2027. Phase 1 Oct 27 ANM Scheme Phase 2 Oct 2032 full connection following completio of new GSP build. | In Progress | 2025-03-01 | 2025-01-27 | Ensured the customer is kept up to date with the project progress and changes. |  | N/A |  | Improved communication, resulting in improved decision making. | Ensures our customers are kept up to date with the proejct development, cost and programme changes. | To continue to hold regular communications with SHEPD | To minimse project misinformation and mitigate programme delays.
Related Action | SSEN/053 | SSEN Transmission | NESO | 24/25 | [13 empty] | Initiated recurring meetings with SHEPD | 2025-01-27 | Business As Usual; Mature | SSEN/053
Co-ordination and cooperation activity | SSEN/054 | SSEN Transmission | SSEN-D, NESO, SPEN | 24/25 | TIA Threshold | Any embedded generator or storage site with a capacity greater the the Transmission Impact Assessment (TIA) threshold is required to undergo a Transmission Assessment. A review has taken place between SSEN Transmission and SSEN Distribtution, SHEPD, to determine whether the TIA threshold for the North of Scotland area could be increased. The Connections Action Plan (CAP) explicitly sets out an action for the TIA thresholds for each network area to be reviewed: “We would also like to see the ESO and DNOs assess and review the thresholds for TIAs; to accelerate connection timescales for distribution customers.” | In Progress | In August 2024, SSEN Transmission published a news article on their website stating that the TIA threshold for SSEN Transmission’s mainland operating area in the north of Scotland could be increased from 50kW to 200kW. SHEPD have been sharing information with SSEN Transmission that allows the impact of the increase in the TIA Threshold to be monitored with a view to identfying any unintended consequences and also opportunities for further change in the TIA Threshold value. | 2024-03-27 | Engaging with SHEPD to receive data on embedded applications that could be affected by a change in the TIA threshold. Joining SHEPD in engagement with affected connection stakeholders to share the benefits and opportunities afforded by the change in the TIA Threshold. | https://www.ssen-transmission.co.uk/news/news--views/2024/8/ssen-transmission-takes-important-step-to-speed-up-new-connections-in-the-north-of-scotland/ | Distribution shared information with Transmission on small embedded customers that have applied to them, so we could understand the impact that a change to the TIA threshold would have. | https://www.ssen.co.uk/our-services/tools-and-maps/embedded-capacity-register/ | Positive - By being able to raise the threshold this means accelerated connection timescales to small embedded customers that will no longer need to undergo a Transmission Impact Assessment | Positive - More efficient data sharing processes and visiblity of embedded generation being set up between SSEN Transmission and SHEPD as part of the ongoing review of the TIA threshold increase impact. | An ongoing review is taking place to understand the impact of the increase of the threshold to 200kW | Co-ordinated datasharing between Transmission and Distribution to allow an increase to the TIA threshold will provide accelerated connection timescales to small embedded customers.
Related Action | SSEN/054 | SSEN Transmission | SSEN-D, NESO, SPEN | 24/25 | [13 empty] | Initial discussion with SHEPD on next steps with TIA threshold and potential for a T/D working group to be set up to deal with issues and to align on wider communications with external stakeholders. | 2025-12-18 | New | SSEN/054
Co-ordination and cooperation activity | SSEN/055 | SSEN Transmission | SSEN-D | 24/25 | T/D Limits | An initiative supported by the ENA involving all TOs and DNOs, that is looking to accelerate the connections of distributed customers where there is potentially unused capacity at a Grid Supply Point (GSP). This has involved weekly meetings and workshops to establish a technical limits calculation methodology and define the eligiblibility criteria for GSPs. With these technical limits agreed at individual GSPs, embedded customers connections can then be accelerated ahead of Transmission reinforcement works through implementation of a DNO owned, automated control scheme such as Active Network Management (ANM). | In Progress | Technical limit connection offers for 42 GSPs produced and sent to NESO as of December 2024. | 2023-04-03 | Engaging with ENA, NESO, TOs and DNOs to agree on the calculation methodology used to establish technical limits at GSP. | https://www.energynetworks.org/publications/grid-supply-point-technical-limits-for-accelerated-non-firm-connections | Distribution shared information with Transmission on the embedded customers connected and looking to connect behind the GSP. This information was used by Transmission to calculate technical limits and fault level headroom at GSPs which was shared back with Distribution through technical limits offers. | N/A | Positive - Allows embedded customers an earlier connection and ability to export to the transmission network on a Non-Firm basis ahead of the completion of required transmission reinforcement works. | Positive - More efficient data sharing processes around embedded generation set up between SSEN Transmission and SHEPD through appendix G process - which has been established as a pre-requisite for technical limits. | Transmission Owner Connection Offers (TOCOs) including technical limits for GSPs have been produced and are awaiting acceptance. Once these are accepted work can commence on the design of the DNO ANM schemes and offers can be made to customers allowing them to accelerate their connection. | A co-ordinated approach between Transmission and Distribution will provide accelerated connection dates to embedded customers.
Related Action | SSEN/055 | SSEN Transmission | SSEN-D | 24/25 | [13 empty] | Regular meetings with ENA lead, Strategic Connections Group consisting of NESO, TO's and DNO's to draft the Technical Limit Rulebook and compliance documentation. | 2024-04-02 | Mature | SSEN/055
Co-ordination and cooperation activity | SSEN/056 | SSEN Transmission | NGET, NESO, Other | 24/25 | GSP Compliance Report | Ongoing and continued collaboration and data exchange between SHEPD and SSEN-T on GSP demand compliance. Assessment is carried out in line with the requirements set out in Grid Code PC.7.4. Whilst this requirement in the Grid Code strictly applies to NGET, SSEN Transmission have adopted a similar approach. SHEPD issue Week24 data to SSEN-T via the NESO on an annual basis, containing schedule 11 (providing demand forecast at the GSPs) and schedule 5 (providing 33kV connectivity diagrams and equipment ratings). SSEN-T use the SHEPD data to calculate current and future demand compliance at each GSP site, in accordance with SQSS section 3. The results are captured within a GSP Compliance Report which is issued back to SHEPD, via the NESO. To support this process SSEN-T and SHEPD are in regular and ongoing communication. | In Progress | SSEN-T's GSP Compliance Report ready for review - end of February 2025 | 2023-01-01 | Ensuring compliance of GSP assets in line with predicted future demand growth. Recognising areas of potential future capacity constraints at GSPs and ensuring upgrades can be planned in a timely manner. | Reports are not openly published rather exchanged directly between SSEN-T, the NESO, and SHEPD. | SEHD share the WEEK24 data on an annual bases with SSEN-T, via the NESO. The Week24 data containts: Shedule 11: One file for each GSP showing the current and forcasted demand (Year 0 - Year 8) at the given GSP during time of GSP peak demand, GB grid peak demand and GB grid min demand. Currently the ubmission does not contain demand for the Access Periods. Shedule 5: Worksheet detailing Nodes, Lines and Transformers as well as single line diagram showing 33kV network and connectivity between the GSPs | Data is not openly published rather exchanged directly between SSEN-T, the NESO, and SHEPD. | Positive - ensures that network / GSPs reamin compliance for demand supply. | Positive - provides us with better understanding of GSP assets and ensures a regular review of emeded demand growth takes place. Improuved communication with SHEPD around GSPs. | Continuation of the annual Week24 and GSP Compliance Reporting process and mentaining ongoing communication and relationship with SHEPD and the NESO on this topic. Agree on GSP Access Groups and establish process for assesign GSP compliance during Access Periods. Create and issue Guidance Notes which document the data-exchange and responsibileties within this process between SSEN-T and SHEPD and can be referenced by both parties. | Some open questions around GSP Access Groups, due to inconsistancies between the curently captured GSP access groups and the 33kV connectivity, as well as the lower transmission voltage levels in the NoS leading to fairly large Access Groups. SSEN-T and SHEPD have discussed these questions and agreed to seek further input from the NESO. As this is a fairly new process for SSEN-T, the structure has evolved slightly to suit requirements over the last two years. Now that strucutre is more defined and established, capturing the steps and data requirements in a Guidance Note, which can also be shared with SHEPD, would be beneficial.
Related Action | SSEN/056 | SSEN Transmission | NGET, NESO, Other | 24/25 | [13 empty] | Regular meetings with SHEPD to discuss Week 24 data and general demand status of GSPs as well as contents of GSP Compliance Assesment. This also extended to NESO/SHEPD/SSEN Transmission discussion of Week 24 submission with respect to demand as an agenda item at the JSDL meeting held on 14/11/2024. | 2024-01-01 | Mature | SSEN/056
Related Action | SSEN/056 | SSEN Transmission | NGET, NESO, Other | 24/25 | [13 empty] | Issuing 2024-25 GSP Compliance Report to SHEPD | 2025-01-01 | Mature | SSEN/056
Related Action | SSEN/056 | SSEN Transmission | NGET, NESO, Other | 24/25 | [13 empty] | Processing of Year 2025 Week24 SEPD data. | 2025-07-01 | Mature; Business As Usual | SSEN/056
Co-ordination and cooperation activity | SSEN/057 | SSEN Transmission | NGET, UKPN, Manitoba Hydro International | 24/25 | TOTEM2 | This project is a continuation of NIA projects, NIA_SHET_0032 TOTEM and NIA_SHET_0035 TOTEM Extension. These projects provided a multi-party agreement that enables the GB TransmissionOwners to work together to acquire and validate a new system model that will enhance, as well as de-risk the integration of new technologies. With the current configuration and capabilities of the TOTEM tool, two aspects currently lead to additional time and effort being required. Firstly, file format conversions are required. Currently, Power Factory model files need to be converted into PSS/E format before they can be uploaded into TOTEM adding additional time and computational effort. Secondly, simulation speeds are considered long taking approximately three hours per scenario. If these additional capabilities aren’t implemented, then we are not maximising the benefits that this tool has the potential to provide. The build-up of knowledge of the impact of control interactions will be limited by the time taken to run a simulation and to convert file types to ensure compatibility. Knowledge of control interactions is vital as the potential for adverse interactions between control devices such as HVDC links and Flexible AC Transmission Systems (FACTS) devices is rising and needs careful consideration within the context of a potentially weaker GB system. | In Progress | The delivery of TOTEM 2 centres around 2 distinct work packages . The latest update March 2026 - The two deliverables have been provided by MHI, however, there are some issues with the dispatch tool is which back with MHI to resolve. This is hoping to be completed in the next few months. 1. Re-Dispatch Tool Refinement - The contractor shall review and refine the existing model re-dispatch tool to enable direct use from Power Factory models, removing the need to convert to PSS/E format. The contractor shall create a comprehensive user manual to enable users to understand both how the tool functions and to apply the tool to re-dispatch network models. The contractor has completed this work package and a final report is due to be submitted for review in February 2025. 2. Simulation Speed Improvement - The contractor shall review the simulation speed of the Scottish network model and make improvements. Optimisation of the model shall be carried out with the aim of simulation times of 10-15 minutes for a 30-second run on a high-performance computer (HPC). The contractor shall create a comprehensive user guide to demonstrate how the optimisation was carried out to enable users to optimise future network models. The contractor has partially completed this work with full completion on track for March 2025. | 2024-05-01 | This project will facilitate the energy system transition and/or benefit consumers in vulnerable situations by developing an accurate modelling framework of the UK's power system. This will ultimately translate into lower energy bills for the taxpayer due to the reduction in unforeseen outages in the electrical power system. | https://smarter.energynetworks.org/projects/nia_shet_0045/?alttemplate=peaprojectpdf | Simulation models and documentation shared between SSEN Transmission and Manitoba Hydro International (MHI). | N/A | This project will make a positive impact on the whole system by accurately modelling any weaknesses that may arise from the interaction of power electronics interfaced devices connected to the grid. Ultimately, the outcomes of this project will make the whole system safer and smarter, thus reducing maintenance costs and electricity bills. | This project will make a positive impact on the assets owned by SSEN Transmission, by accurately modelling any weaknesses that may arise from the interaction of power electronics interfaced devices connected to the grid. | The recommended next stage is to complete this project and consider whether further developments are required in the modelling framework. | The benefits of accurately modelling the power system are very significant and power system modelling is key to understanding and predicting any underlying issues in the electrical power grid.
Related Action | SSEN/057 | SSEN Transmission | NGET, UKPN, Manitoba Hydro International | 24/25 | [13 empty] | Purchase order to Manitoba Hydro International issued on September 20254 for simulation speed enhancement of TOTEM 2. | 2024-05-17 | Mature | SSEN/057
Co-ordination and cooperation activity | SSEN/058 | SSEN Transmission | SPEN, NPL, ICL | 24/25 | SYSMET Alpha Phase | SYSMET Alpha phase provides a system strength measurement and estimation to enable detection and mitigation of weak system conditions and instability associated with increased connection of inverter-based resources (IBR). The overall objective of the Alpha Phase project is to enable implementation of online system strength monitoring based on frequency-dependent impedance measurement in the GB power system, by doing the following activities: - Developing detailed standardised specifications for high-voltage injection equipment and measurement systems. - Assessing the suitability of existing network assets against specifications. - Identifying candidate implementation locations. - Developing detailed standardised specifications for algorithms to evaluate impedance and system strength metrics from measurement data. - Determining the required injection level considering real grid characteristics. - Assessing integration with existing monitoring and modelling systems in terms of data flows, communications, and visualisation. - Identifying technology partners for implementation of hardware and software requirements. - Developing validation methods to verify the accuracy of new system strength monitoring solutions. - Understanding governance processes for field implementation including network approvals, and compliance with grid codes and standards. | Complete | 28-January-2025: Mid-point project review with UKRI. The latest update March 2026 - SYSMET are currently preparing for a Beta Phase (SYSMET actviity added to refelct this 25/26) application which is targeted for June 2026. This is following the completion of the Alpha (and a decision to delay the Beta submission to mid-2026). The Beta phase will be delivered in collaboration with NPL, Imperial College London, SPT, UKPN, SSE Renewables and likely NESO. Work package development continues to refine the passive and active frequency-dependant impedance measurement methods and their evaluation in PSCAD and HIL environments. | 2024-05-24 | SYSMET helps proactively identiy potential oscillations or low stability margins in the network, thus avoiding a potential disconnection and loss of electricity supply to the end user. Therefore, SYSMET reduces the risk of unforeseen interruptions in the electricity supply and provides a lower cost of electricity bills to the taxpayer. | N/A | The project consortium regularly has MS Teams meetings and in-person meetings. Several documents and a simulation computer model in PSCAD has been produced by the consortium and shared among consortium members. | N/A | SYSMET makes a positive impact on the whole system by reducing unforeseen interruptions in the supply of electricity to the end user. | SYSMET makes a positive impact to the assets owned by SSEN Transmission, by reducing the probability of equipment damages arising from sustained, growing oscillations in the power system. | The next stage for SYSMET is to continue to a SIF Beta phase application, in order to implement the methods proposed by the projects in a real-world installation, thus proving the potential benefits this will bring to the UK's power system in terms of stability and power quality. | SYSMET is key to ensuring the stability of the power system and to implement a smooth transition to a net-zero electrical power system in the UK.
Co-ordination and cooperation activity | SSEN/059 | SSEN Transmission | SSEN-D, NESO; ICL | 24/25 | GSP Modelling | The impacts of distribution networks on power system behaviours are increasing due to the rapid reduction of system strength and the increase of distributed resources. The GB system has been using static ZIP (i.e., Z:impedance, I:current, P:power) models to represent distribution networks at the grid supply point (GSP), which may no longer be satisfactory for stability and fault studies. It is known that distribution networks may influence the damping of oscillations and induce delayed voltage recovery due to the transient overcurrent of induction motors. With the current limitation of the inverter-based resources, there is a risk that delayed voltage recovery may propagate wider into the system and evolve into a fault-induced voltage collapse. Distribution networks may also supply fault current back into the GSP and therefore affect the protection schemes at the transmission level. This project sets out to establish GB-wide composite load models as seen at GSPs and develop methodologies to verify such models in the field. | In Progress | SSEN Transmission internal funding approvals were completed in December 2024, the project consortium is currently producing the necessary documentation in order to formally kick-off the project in March 2025. The latest update March 2026 - The project is away to kick off (after delays with recruitment at the university). Initially a literature review (both academic and industrial) will be completed. Development of methodologies will be designed to enable more accurate model representation at the grid supply point from the distribution side. These tasks shall take approximately 12 months. | 2024-08-18 | Developing more accurate GSP models will minimise any unforeseen power system oscillations or interruptions in electricity supply, which will ultimately benefit the power system as a whole by reducing electricity bills and unplanned outages. | N/A | Project scope documents have been shared within the project consortium, which includes transmission owners and academic institutions. | N/A | This project will make a positive on the whole system by reducing any unforeseen outages or interruption in the supply of electricity, and consequently will reduce the electricity bill of the taxpayers. | This project will make a positive impact on SSEN Tranmission assets. By developing more accurate GSP models, any unforeseen outages of assets owned by SSEN Transmission will be minimised. | The next stage of this project is the formal project kick-off in March 2025. | The recommendation for this project is to proceed to project kick-off as planned in March 2025.
Related Action | SSEN/059 | SSEN Transmission | SSEN-D, NESO; ICL | 24/25 | [13 empty] | Detailed proposal drafting by Imperial College London completed. SPEN and NESO have also been invited to be part of the project. | 2025-01-08 | New | SSEN/059
Related Action | SSEN/059 | SSEN Transmission | SSEN-D, NESO; ICL | 24/25 | [13 empty] | Initially a literature review (both academic and industrial) will be completed. Development of methodologies will be designed to enable more accurate model representation at the grid supply point from the distribution side. These tasks shall take approximately 12 months. | 2026-03-31 | New | SSEN/059
Co-ordination and cooperation activity | SSEN/060 | SSEN Transmission | SSEN-D | 24/25 | Shetland on-island transmission network strategy | SSEN Transmission collaborated with SSEN Distribution, the Shetland Island Council, the North Sea Transition Authority (NSTA), ScotWind developers, and other significant stakeholders to conduct a comprehensive optioneering exercise exploring various future energy pathways extending to 2045. This initiative has established our preferred strategy for a Shetland on-island transmission network, adhering to our Area System Planning (ASP) methodology. The chosen approach represents the most cost-effective and efficient solution, capable of accommodating all viable pathways through 2045, aligning with Scotland's net zero objectives, while also minimizing infrastructure to lessen the impact on the environment and local communities. | In Progress | Final preferred strategy was presented to the Shetland Island Council (and other key stakeholders, including SSEN Dsitribution) on 10th Dec 2024. 29/01/26 Continued engagement with the stakeholders mentioned and we have been working closely with SSEN Distribution on their optioneering for their updated strategic development plan on Shetland. | 2023-06-01 | Stakeholder inputs, including SSEN Distributions view on future GSP requirements on Shetland, were direct inputs into our optioneering approach, which helped us to determine a preferred approach which can accomodate all potential future and known requirements on Shetland for Net Zero. | The Shetland on-island transmission infrastructure project has been submitted to Ofgem as part of our CP2030 submission - to obtain approval for need and preffered option (Engineering Justification Paper has been provided) | To inform our year round assessment of network requirements on Shetland, SSEN Distribution provided year round demand profiles for the Gremista GSP, and informed us of potential future plans on Shetland, which included the possbility of a GSP on Yell. | N/A | Positive - ensured our preferred approach considered future SSEN Distribution requirements out to 2045 (and beyond) | Positive - GSP demand profile information is beneficial for SSEN Transmission as it enables us to ensure that our transmission system is equipped to meet future demand while efficiently maintaining compliance with GSP standards. | The information shared by SSEN Distribution is now being used to inform GSP limits and generation curtailment projections (this is covered in the 'Shetland ANM - curtailment assessment' activity) to provide better information and certainty to islanded customers. | Working closely with SSEN Distribution has informed our preferred on-island transmission strategy for Shetland, and the learnings/data from this has been used to inform the Shetland ANM scheme and curtailment assessment exercise.
Co-ordination and cooperation activity | SSEN/061 | SSEN Transmission | NGET; SPT; NESO; Other | 24/25 | Shetland ANM - Curtailment Assessment | After determining our preferred design for the Shetland on-island transmission strategy (delivery date 2032), SSEN Transmission, utilising distribution/demand profile data provided by SSEN Distribution, undertook a generation curtailment assessment to understand the likely operation of the Shetland Active Network Management (ANM) scheme and to assess the future associated impact of the Shetland 2nd HVDC link and Shetland ScotWind connections on network access for small scale distributed connected projects (to inform their business case). The outcome of the curtailment assessment has been shared with SSEN Distribution for them to provide follow-on information to their customers directly, and to answer any queries. This work has also helped to identify the early operational philosophy of our transmission ANM scheme, and it's interaction with SSEN Distribution systems. | Complete | February 2025. 29/01/26 Following confirmation of the transmission and distribution queue in Shetland through the connections reform process there is no need to update this curtailment assessment. | 2024-07-01 | This activity was important in order to provide distribution customers with a future outlook of network access on Shetland, to inform their business case for network connection. SSEN Distribution had many queries from multiple customers on the impact of the future transmission system (and associated Shetland ScotWind connection) on their network connection. | SSEN Transmission curtailment assessment report and associated data spreadsheet provided to SSEN Distribution (internal) | SSEN Transmission curtailment assessment report and associated data spreadsheet provided to SSEN Distribution (internal) - curtailment assessment carried out (utilising SSEN Distribution generation/demand profiles, with SSEN Transmission generation profiles) against 5 different future scenarios to provide each distribution customer with an annual curtailment range from 2032 onwards. | SSEN Transmission curtailment assessment report and associated data spreadsheet provided to SSEN Distribution (internal) | Positive - SSEN Distribution and distribution customers are more informed about likely transmission network access before/after connection of Shetland ScotWind (which should encourage connection) | Positive - proactive engagement with SSEN Distribution to provide the information nescesarry for them to answer difficult customer queires on future network access. | SSEN Distribution have some further sensitivities that they want to explore in the curtailment assessment, and work will continue to address any further queries from SSEN Distribution and their customers. | This collaborative analysis with SSEN Distribution has helped to identify the early operational philosophy of our transmission ANM scheme on Shetland, and it's interaction with SSEN Distribution systems.
Co-ordination and cooperation activity | SSEN/063 | SSEN Transmission | SSEN-D, NGET, SSEN-T, NESO | 24/25 | North of Beauly DLR | Planning and discussions with NESO related to communication of day ahead ratings calculated from DLR technology. This will enable the NESO to reduce curtailment of renewable energy on the network. | Complete | August 2024 discussion with NESO around expectations. August 2024 discussion with NESO around expectations. 19/1/26 evolved into network rating management system. DLR is now BAU, now evolved into work with NESO. This activity is complete, but we will continue to follow updates. | 2022-02-01 | We expect that the activity will contribute to efficiency of power transmission across the relevant area of the network. Through coordination with NESO we hope to have a coherant plan for communication of the data | N/A | N/A yet shared but discussions have indicated that day ahead rating will be communicated via standard rating sheet | N/A | Positive - reduced contraint costs as infrastructure used to its maximum efficiency | Neutral - we will learn how to communicate DLR to NESO and some additional benefits of onitoring on our network | Continue discussions and then initiate transfer of data with final action of NESO engaging the dynamic rating | Recommended to complete the planning and discussions as this will save the consumer considerable cost saving as well as monitoring of the lines
Related Action | SSEN/063 | SSEN Transmission | SSEN-D, NGET, SSEN-T, NESO | 24/25 | [13 empty] | Coordinate the process of data transfer and plans for future iterations | 2024-11-04 | Improving | SSEN/063
Co-ordination and cooperation activity | SSEN/064 | NESO | SSEN-T, SPT, NGET, Other | 24/25 | Virtual Energy System Data Sharing Infrastructure | NESO have initiated a Data Sharing project to create a common infrastructure to achieve an ecosystem of connected digital twins, as we transition to net zero. It is expected that this will create process efficiencies | Complete | January 2025 the SSENT element of the project started. January 2025 the SSENT element of the innovation project started 19/1/26 and completed in August 2026. Although the Innovation project has now completed there is some addiotional collaboration ongoing between SSENT data team and other Networks. The Innovation involvement has now ended. | 2024-09-02 | Efficiencies will be achieved through coordination with the other Networks | https://smarter.energynetworks.org/projects/nia2_ngeso081/ https://smarter.energynetworks.org/projects/nia_shet_0053/ | Test data in spreadsheets and direct input | N/A | Positive - improved collaboration and investment in safety, grid resilience, less error prone outage management, interoperability, reduction in data redundancy, delivery of open data | Positive - improved safety, grid resilience, less error prone outage management, interoperability, reduction in data redundancy, delivery of open data | Continue with standalone SSENT project that interacts with the overarching NESO project | This activity will provide benefits to the business, other networks and the consumer
Related Action | SSEN/064 | NESO | SSEN-T, SPT, NGET, Other | 24/25 | [13 empty] | Perform all activities involved with standalone SSENT project (NIA_SHET_0053) and continued involvement in NESO project (NIA2_NGESO081) | 2024-09-11 | New | SSEN/064
Co-ordination and cooperation activity | SSEN/065 | National Grid | SPEN; DNV, University of Manchester | 24/25 | SF6 Whole Life Strategy SIF Beta | Project, led by NG to develop an economic, efficient, and holistic strategy for delivering an SF6-free electricity system that will support GB’s ambition to deliver a net-zero, resilient energy system. | In Progress | SIF Alpha phase completed April 24. SIF Beta project started November 2024. Progressing according to plan with updates published on the Smarter Networks portal (January 2026). | 2023-04-03 | Efficiency will be achieved as well as some cost savings due to reduction in SF6 leakage and use | https://smarter.energynetworks.org/projects/ukri10084569/ | Test data, SF6 volumes and other pertinent technical information. | N/A | Positive - reduces cost and improved efficiency | Positive - reduces cost and impovedment of efficiency | Maintain involvement in the project | Continued engagement in the project ensures SSENT receive outputs that they can use on their network as well as being able to influence the decision making.
Related Action | SSEN/065 | National Grid | SPEN; DNV, University of Manchester | 24/25 | [13 empty] | Maintaining engagement with the project and providing appropriate internal subject matter expertise to support the project progress. | 2024-11-01 | Improving | SSEN/065
Co-ordination and cooperation activity | SSEN/066 | SSEN Transmission | SSEN-T, SSEN-D, NGET, SPEN, Other | 24/25 | BLADE | The overarching aim of the project is to bring electricity system restoration from offshore wind to commercial reality by building the necessary cross-industry understanding including onshore transmission network owners, transmission system operators, offshore wind farm operators, and technology suppliers. This will improve economy and efficiency across the grid | In Progress | SIF Beta stage began September 2024. Progressing according to plan with updates published on the smarter networks portal, update January 2026. | 2023-04-03 | The outputs from the project are expected to provide both economic and security improvements across the grid through involvement of offshore wind in restoration activities | https://smarter.energynetworks.org/projects/sif_blade_beta/ | Test data and some open network information | N/A | Positive - improves efficiency and ability to restore the networks | Positive - improves efficiency | Maintain involvement in project, providing input and reviewing outputs until project closes in October 2027 | By retaining involvement in the project we ensure that SSENT remains informed on the outputs.
Related Action | SSEN/066 | SSEN Transmission | SSEN-T, SSEN-D, NGET, SPEN, Other | 24/25 | [13 empty] | Maintain involvement in the project until closure in October 2027 | 2024-09-02 | Improving | SSEN/066
Co-ordination and cooperation activity | SSEN/067 | Ofgem | SSEN-T, SPT, NGET; UKRI, Ofgem, SGN | 24/25 | Ofgem Innovation RIIO3 working group | Working group initiated by Ofgem to assess the direction, change requirements and challenges related to the innovation funding mechanisms in T3. It is expected that this will improve the efficiency of innovation activities going into T3 | Complete | March 2026 working group assessed the requirements for SIF and potential deployment funding mechanism. RIIO T3 working group has now concluded its work in advance of RIIO T3. (Update January 2026) | 2024-12-09 | Efficiency of T3 innovation project processes through coordination with other Networks | N/A available | Pland and proposed processes | N/A | Positive - improved efficiency through collaboration and cooperation on activities by all Networks | Positive impact as UK Innovation funding strategy can be better understood and influenced | Agreement on T3 funding mechanism processes | This will help to enhance the process of T3 innovation funding requests and increase efficiency
Related Action | SSEN/067 | Ofgem | SSEN-T, SPT, NGET; UKRI, Ofgem, SGN | 24/25 | [13 empty] | Continue engagement with T3 Ofgem working group | 2024-12-10 | New | SSEN/067
Co-ordination and cooperation activity | SSEN/068 | NESO | SSEN-T, NGET, SPT, Other | 24/25 | Electricity Transmission Design Principles (ETDP) | SSEN Transmission particpates in the work group set up by NESO in response to the Electricity Commissioner's recommendation to establish a set of Electricity Transmission Design Principles. The work group membership comprise NESO, the three onshore TOs and variuos other stakeholders. As well as joining and contributing to work group meetings we have attended two face-to-face workshops to discuss drafts of the proposed Strategic, Substation Design and Technology principles. We have also held joint meetings withthe other TOs to cordinate comments and feed back on the draft principles to NESO. Thius acitivty is aimed at collaborating withthe NESO to help them prepare proposed priciples for consultation later in 2025. 29/01/26 Still ongoing. ETDP has been consulted upon. 3 new actions added to this activity. | In Progress | Live' testing of the Substation Design and Technology principles on three representative TO projects to identify potential issues, gaps or unintedned consequnces associted with adoption of the draft proposed ETDP | 2024-07-15 | This activity is partially aimed at achieving a consistent, endorsed approach with regard to approach to transmission design that can be referred to by all TOs. This should give more weight to design decisions that have been arrived at through application of the ETDP and thus provide some defence against potential objections raised during the consenting process and, in turn, helping deliver tranmission capacity in a more timely manner. | https://assets.publishing.service.gov.uk/media/64c8e96e19f5622360f3c0f0/electricity-networks-commissioner-letter-to-desnz-secretary.pdf refer Recommendation 8 | Information exchange has been narrative via NESO MS Powerpoint presentations and MS word documents setting out the draft priciples at various stages of their evolution | N/A | Positive; the activity helped foster alignment among TOs with respect to Transmission early design. The transparency the activity will give to the design rocess used by the TOs and NESO will hlep bring effciency in the delivery of transmission projects through the palnning process. | Neutral; the activity will help highlight the reason we follow the existing we deploy methods in developing transmission projetcs and set this in the context of consistency of assumptions and approaches across GB TOs. This will be beneficial when engaged in dialogue with community and planning stakeholders. | Next Stage is completion of the joint TO testing of the draft principles followed by publication of the public consultation on the ETDPs. Towards the end of 2025/start of 2026 it is expected that the ETDP wil be granted final approval and then used as part of the development of Transmsission Projects across all TO licnce areas within GB. | This activity will deleiver the Electicity Comissioner's recommendation aimed at streamlining and promoting consistentcy across GB network owners with respect to rapid delivery of critical strategic national transmission infrastructure.
Related Action | SSEN/068 | NESO | SSEN-T, NGET, SPT, Other | 24/25 | [13 empty] | Consultation document prepared and produced by NESO. Actions, reviewing and commenting on | 2025-06-14 | Improving | SSEN/068
Related Action | SSEN/068 | NESO | SSEN-T, NGET, SPT, Other | 24/25 | [13 empty] | Reviewing and commenting on NESO's consultation document and subsequently we responded to the consultation. | 2025-06-16 | Improving | SSEN/068
Related Action | SSEN/068 | NESO | SSEN-T, NGET, SPT, Other | 24/25 | [13 empty] | Continued to attend working group meetings on ETDP. | 2025-05-15 | Business As Usual; Mature | SSEN/068
Co-ordination and cooperation activity | SSEN/069 | Other | SPEN, NGET, SSEN-T, Ofgem, DESNZ | 24/25 | Centralised Strategic Network Plan (CSNP) | NESO are developing the methodology for the Centralised Strategic Network Plan (CSNP). This will be the enduring process which approves large-scale transmission infrastructure in GB. This has involved attending a series of workshops (estimated total workshop commitment: ~65 hours) as well as having senior representation on a steering group. SSEN Transmission's involvement has been to provide detailed information on how transmission licensees develop large capital projects, participate in discussions on methodology development, and challenge NESO thinking. | In Progress | Ongoing. 29/01/26 We continue to engage with NESO, as well as other Transmission Owners, NESO and DESNZ as part of the wider efforts to establish the CSNP methodology. From 1st April 25 to 1st April 26 we have attended semi-regular workshops/forums coordinated by NESO (estimated working time: ~50 hours). In this time NESO have published a draft methodology which we responded to in full (Q2 2025). We have also reviewed and fed back on subsequent revisions to this draft methodology (Q1 2026). | 2024-04-17 | This activity is determining the methodology which will approve all future electricity transmission infrastructure. This impacts the full electricity transmission system and has consequential impacts for other energy vectors, e.g. hydrogen, gas. | https://www.neso.energy/document/349136/download | NESO have produced a large volume of packs to support this activity. These are restricted in access, only available on a NESO-controlled SharePoint. | Not available to share outwith restricted NESO platform. | This activity is determining the methodology which will approve all future electricity transmission infrastructure. This impacts the full electricity transmission system and has consequential impacts for other energy vectors, e.g. hydrogen, gas. | Positive. The CSNP will be an essential process for SSEN-T as a licensed TO, so being able to shape the methodology development is positive. | Continue to engage in discussions with NESO. Next milestons: Draft methodology chapter reviews (May 2025). Formal methodology consultation (June 2025). | We should continue to engage on the basis that it supports the development of a methodology which will have a significant impact on SSEN-T.

## Glossary
Acronym | Description
AC | Alternating Current
ANM | Active Network Management
ASP | Area System Planning
BEIS | Department for Business, Energy & Industrial Strategy – former UK government department responsible for energy policy and strategy.
BESS | Battery Energy Storage System
CAP | Connections Action Plan
CBAs | Cost Benefit Analyses
CP2030 | Clean Power 2030
CUSC | Connection and Use of System Code
DC | Direct Current
DCCB | Direct Current Circuit Breaker
DESNZ | Department for Energy Security and Net Zero
DNO | Distribution Network Operator – licensed operator of regional electricity distribution networks.
DNV | DNV (independent assurance and energy consultancy; formerly Det Norske Veritas).
DSO | Distribution System Operator
ECR | Embedded Capacity Register
EJP | Engineering Justification Paper
ENA | Energy Networks Association – UK trade body representing electricity and gas network operators.
ENIT | Energy Networks Innovation Taskforce
ESO | Electricity System Operator
ETYS | Electricity Ten Year Statement
FACTS | Flexible AC Transmission Systems
FES | Future Energy Scenarios
G2tWQ | Gate 2 to Whole Queue (Connections Reform Process)
GB | Great Britain
GSP | Grid Supply Point – substation/interface where the transmission network supplies the distribution network.
HIL | Hardware‑in‑the‑Loop
HND | Holistic Network Design
HNDFUE | Holistic Network Design Follow‑Up Exercise
HOWSUM | Hebrides and Orkney Whole System Uncertainty Mechanism
HPC | High Performance Computer
HVDC | High Voltage Direct Current – technology used for high-capacity electricity transmission, often for subsea links and offshore integration.
IBR | Inverter-Based Resources
ICL | Imperial College London – university/research partner referenced in the register.
ITA | Independent Technical Advisor/Assessor – provides independent technical review/assurance for projects, funding or regulatory submissions.
JPC | Joint Planning Committee
LAEP | Local Area Energy Plan
LHESS | Local Heat and Energy Efficiency Strategy
NARM | Network Asset Risk Metric
NESO | National Energy System Operator – Great Britain’s electricity system operator (successor organisation to NGESO).
NGESO | National Grid Electricity System Operator – former Great Britain electricity system operator (predecessor to NESO).
NGET | National Grid Electricity Transmission plc (GB electricity Transmission Owner for England & Wales).
NIA | Network Innovation Allowance
NOA | Network Options Assessment
NPL | National Physical Laboratory
NSTA | North Sea Transition Authority – UK regulator for offshore oil & gas, hydrogen and carbon storage industries.
OHL | Over head line
OWF | Offshore Wind Farms
PSCAD | Power Systems Computer‑Aided Design
PSL-FC | Preferred Solutions to perform for Lower levels of Fault Current on AC network
PSS/E | Power System Simulator for Engineering
RDP | Regional Development Plan
REACT | Rapid Evaluation Areal Connection Tool
RESP | Regional Energy Strategic Plans
RIIO | T3 Revenue = Incentives + Innovation + Outputs – Transmission, Price Control Period 3
SEP | Strategic Energy Planning
SGN | SGN – Scotland Gas Networks (gas distribution network operator and stakeholder for gas–electricity coordination).
SHEPD | Scottish Hydro Electric Power Distribution – the northern Scotland electricity distribution licence area within SSEN Distribution.
SIC | Shetland Islands Council – local authority stakeholder referenced for island/offshore developments.
SIF | Strategic Innovation Fund
SPEN | Scottish Power Energy Networks (ScottishPower’s electricity network businesses, including distribution and transmission operations).
SPT | Scottish Power Transmission plc (GB electricity Transmission Owner for central and southern Scotland).
SQSS | Security and Quality of Supply Standard
SSEN-D | Scottish and Southern Electricity Networks Distribution (electricity Distribution Network Operator, SSEN Distribution).
SSEN-T | SSEN Transmission (Scottish and Southern Electricity Networks Transmission; electricity Transmission Owner in the north of Scotland).
SSEP | Strategic Spatial Energy Plan
STATCOM | Static Synchronous Compensator
STC | System Operator – Transmission Owner Code
SYSMET | System Strength Measurement and Evaluation
tCNAIM | Transmission Common Network Asset Indices Methodology
tCSNP2R | Centralised Strategic Network Plan 2 Refresh
TIA | Transmission Impact Assessment
TNUoS | Transmission Network Use of System
TO | Transmission Owner – licensed owner/operator of electricity transmission assets.
TOTEM 2 | Transmission Owner Tools for EMT Modelling 2
UKPN | UK Power Networks – electricity Distribution Network Operator serving London, the East and South East of England.
UKRI | UK Research and Innovation – UK public body that funds and supports research and innovation programmes.